## Mokėjimo sąlygos
27771-2 Services of design and design implementation supervision of the Rail Baltica railway infrastructure maintenance depot in Kaunas
Phases of workflow | Entry No. | Service phases and works | Fact of payment (product) or condition and amount to be paid, EUR **
Condition/fact: The Designer shall apply in writing to the Customer for the payment of the advance not later than 5 (five) days after the entry into force of the Contract. Maximum amount of advance payable: up to 30% of the maximum Contract price in advance
Phase I | 1.1 | Preparation of the inception report, reconciliation | Condition/fact: Documents prepared and submitted by the Designer and approved by the Customer, including but not limited to the Inception Report, Project Implementation Plan, Project Risk Management Plan, Schedule for the Provision of Design Services (Gantt Chart) Amount payable: 100% of the total cost of these works (excluding VAT)
| 1.2 | Preparation and coordination of engineering geodetic and topographical surveys | Condition/fact: Topographical survey report submitted by the Designer and approved by the Customer Amount payable: 100% of the total cost of these works (excluding VAT)
| 1.3 | Other necessary studies according to the specifics of the object to be procured | Condition/fact: Report of other studies submitted by the Designer and approved by the Customer. Amount payable: 100% of the total cost of these works (excluding VAT)
Phase II | 2.1 | Preparation, coordination and receipt of the assessment report of the Lithuanian Geological Survey for Phase I engineering geological surveys (in accordance with RBDG-MAN-041-0100 – Requirements for site investigations, Phase 1.1) | Condition/fact: A geological survey report submitted by the Designer and approved by the Customer, including obtaining an assessment by the Lithuanian Geological Survey Amount payable: 40% of the total cost of these works (excluding VAT)* After the customer has provided the source material (topographic photo with borehole locations and goelogical lithological borehole columns with goetechnical sounding) for boreholes of up to 6 m. 40% of the total price (excluding VAT)* After the Client has provided the source material ( topographic photo with borehole locations and goelogical lithological borehole columns with goetechnical sounding) for boreholes from 6 to 50 m. 20% of the total price (excluding VAT)* After the Client has provided the survey evaluation approved by the Lithuanian Geological Survey.
| 2.2 | Preparation and coordination of a geotechnical report | Condition/fact: A geotechnical investigation report submitted by the Designer and approved by the Customer. Amount payable: 100% of the total cost of these works (excluding VAT)
| 2.3 | Preparation of design proposals, including coordination, approval, publicity and obtaining the building permit | Condition/fact: Design proposals approved by the Customer (after public information procedures, approval of the design proposals by the municipal administration, receipt of all special requirements, connection conditions, approvals, consents, written consents) and building permit; Amounts payable: 1) 80% of the total cost of the fees for these works (excluding VAT)* after the design proposals have been approved by the Employer (after public information procedures have been carried out, after the design proposals have been approved by the municipal administration, and after all the special requirements, conditions of connection, approvals, consents, and written approvals have been obtained); 2) 20% of the total cost of the quotations for these works (exclusive of VAT)* after the Designer has transferred the obtained building permit documents to the Customer.
| 2.4 | All necessary special requirements, conditions of connection, approvals, consents, written consents, etc. have been obtained.
| 2.5 | Digital model data (corresponding to the level of detail of the design proposals in accordance with the requirements of the RB DG and the Customer) prepared, coordinated and approved | Condition/fact: Digital model data provided by the Designer and approved by the Customer. Amount payable: 100% of the total cost of the rate for these works (excluding VAT)
Phase III | 3.1 | Preparation, coordination and receipt of the assessment report of the Lithuanian Geological Survey for the Phase II engineering geological survey (in accordance with RBDG-MAN-041-0100 – Requirements for site investigations, Phase 1.2) | Condition/fact: A geological survey report submitted by the Designer and approved by the Customer, including obtaining an assessment by the Lithuanian Geological Survey Amount payable: 40% of the total cost of these works (excluding VAT)* After the customer has provided the source material (topographic photo with borehole locations and goelogical lithological borehole columns with goetechnical sounding) for boreholes of up to 6 m. 40% of the total price (excluding VAT)* After the Client has provided the source material ( topographic photo with borehole locations and goelogical lithological borehole columns with goetechnical sounding) for boreholes from 6 to 50 m. 20% of the total price (excluding VAT)* After the Client has provided the survey evaluation approved by the Lithuanian Geological Survey.
| 3.2 | Revision and coordination of the geotechnical report | Condition/fact: A geotechnical investigation report submitted by the Designer and approved by the Customer. Amount payable: 100% of the total cost of the rate for these works (excluding VAT)
| 3.3-3.27 | Preparation and coordination of the technical detailed design. (Preparation and coordination of the technical detailed design for structures and/or engineering networks (Serial No. 3.3-3.27) of the sizes set out in the table of prices and fees (Annex 1). | Condition/fact: The Designer shall submit to the Customer the documentation of the technical design of the work (executed to a high standard in accordance with all requirements, building regulations) in the prescribed design form. Amount payable: 1) 40% of the total cost (excluding VAT) of the following fees (preparation, coordination of the technical detailed design) * upon receipt of the documentation of the technical detailed design in accordance with the prescribed composition of the project for the first review. 2) 40% of the total price (excluding VAT) of the fees for the following works (preparation and coordination of the technical detailed design) * upon submission of revised documentation in accordance with the technical detailed design, as agreed by the Customer and other coordinating authorities, third parties, in accordance with the prescribed composition of the project, for expert assessment.
| 3.28 | Digital model data (corresponding to the level of detail of the technical detailed design in accordance with the requirements of the RB DG and the Customer) prepared, coordinated and approved | Condition/fact: Digital model data provided by the Designer and approved by the Customer. Amount payable: 100% of the total cost of the rate for these works (excluding VAT)
| 3.29 | Performed expert examination of the technical detailed design | Condition/fact: The Designer shall obtain and submit to the Customer a positive conclusion of the evaluation of the hazard analysis and the technical specification for interoperability. Upon receipt by the Designer (in accordance with Clause 3.3 of the Special Terms and Conditions of the Contract) of a positive expert report and approval by the Customer of the technical detailed design. Amount payable: 20% of the total price (excluding VAT)* of the total price (excluding VAT) of the fees provided in Clauses 3.3 to 3.27 for the works (preparation, coordination, approval of the technical detailed design)
| 3.30 | Technical detailed design approved by the customer
| 3.31 | Assessment and management of hazard analysis (AsBo) and assessment of compliance with the requirements of the technical specification for interoperability relating to the infrastructure subsystem of the railway system (NoBo)
Phase IV | 4.1 | Project supervision | Payments will be made in accordance with a separately submitted and coordinated schedule of payments for project supervision services at the commencement of the works of the Contract
* Procurement of design services on an as-needed basis, up to the maximum portion of the Contract price allocated for the procurement of such Services.
** The amount of the advance paid shall be deducted from amounts due to the Designer in accordance with Clause 4.7. of the Contract.