# RATIONALE AND THE NEED OF THE PROCUREMENT

  - Joint stock company Lithuanian Airports (hereinafter – the Buyer) seeks to acquire the following services related to the baggage handling system for the new Arrivals Terminal T5 at Vilnius Airport (hereinafter – T5 Arrivals BHS):

Technical specification preparation and system Design services – 3D BIM model.

Technical supervision of the project and technical quality assurance services.

## Scope of the Services

      - The Buyer seeks to ensure the quality of the System being installed and acquire the project technical support and project quality assurance services.

      - Technical specification preparation and system Design services of T5 arrivals BHS must include:

        - Expert consultations during the design phase (BHS layout, BHS supplier and BHS equipment selection, BHS capacity and other with baggage arrivals system related questions);

        - Cooperation with the designers and architects of the T5 Arrivals Terminal in the design of the T5 Arrivals BHS;

        - Evaluation of Buyer needs;

        - Airport and BHS capacity requirements evaluation;

        - Passenger flow growth analysis;

        - Peak time periods analysis;

        - Passenger flow analysis;

        - BHS maintenance analysis;

        - Security and customs process and measures analysis;

        - Building analysis – passenger flow analysis, waiting area analysis, BHS dedicated area analysis;

        - Baggage trolley movement and baggage loading analysis;

        - BHS design (layout in 2D & 3D BIM format);

        - Other services necessary to design T5 arrivals BHS in T5 arrivals terminal.

        - Technical specifications as minimum must include (these topics must cover in a detailed way, with a goal to do not limit product selection):

          - GLOSSARY OF TERMS

          - INTRODUCTION

            - GENERAL

            - BHS CONTRACT DRAWINGS

            - PROJECT REQUIREMENTS

            - PROJECT SUBMITTALS

            - SCOPE AND DELIVERY REQUIREMENTS

            - SITE CONSTRUCTION

            - EXECUTION REQUIREMENTS

          - SCOPE OF WORKS

            - SCOPE OF WORKS TABLE

          - BHS DESIGN

            - GENERAL BHS REQUIREMENTS

            - PHASED INSTALLATION WORKS

            - ARRIVALS BAGGAGE SCREENING

            - SCREENING EQUIPMENT – PROVIDED BY OTHERS

          - PERFORMANCE REQUIREMENTS

            - BHS THROUGHPUT

            - NORMAL IN GUAGE (IG) BAGGAGE CHARACTERISTICS

            - OUT OF GAUGE BAGGAGE

            - SYSTEM AVAILABILITY

            - BAG JAM FREQUENCY

            - NOISE LEVELS

          - EQUIPMENT AND SYSTEM KEY REQUIREMENTS

            - ENVIRONMENTAL CONDITIONS

            - ELECTRICITY REQUIREMENTS

            - HOURS OF OPERATION

            - LAYOUT REQUIREMENTS

            - QUEUE CONVEYOR REQUIREMENTS

            - CONVEYOR SPEEDS

            - STATIC & DYNAMIC EQUIPMENT LOAD REQUIREMENTS

            - EQUIPMENT FINISHES

          - DESIGN COORDINATION AND DESIGN REQUIREMENTS

            - PROVIDE APPROPRIATE ACCESS

            - INTERFACE WITH BUILDING STRUCTURE

            - PERSONNEL SAFETY

          - MAINTAINABILITY

            - DESIGN OF THE COMPONENTS

            - MAXIMUM MAINTENANCE TASK TIMES

            - AVAILABILITY OF CONSUMABLES AND REPLACEMENT PARTS

            - LIFESPAN

            - COMPONENT STANDARDIZATION AND INTERCHANGEABILITY

            - NAMING CONVENTION (EQUIPMENT IDENTIFICATION)

          - CODES AND STANDARDS

            - REGULATIONS

            - IATA STANDARDS

            - ICAO STANDARDS

            - INTERNATIONAL STANDARDS ORGANISATION (ISO)

            - EUROPEAN STANDARDS

            - VILNIUS AIRPORT STANDARDS

          - EQUIPMENT SPECIFICATIONS

            - CONVEYOR EQUIPMENT

            - ANGLE RECLAIM CAROUSELS

            - ROLLER SHUTTER FIRE AND SECURITY DOORS

            - STEELWORK, PLATFORMS, WALKWAYS, STAIRS AND LADDERS

          - LOW LEVEL CONTROLS (LLC) SYSTEM

            - KEY REQUIREMENTS

            - GENERAL ELECTRICAL REQUIREMENTS

            - PROGRAMMABLE LOGIC CONTROLLERS (PLC)

            - WIRING DEVICES

            - PHOTOCELLS (PHOTOELECTRIC SENSORS) (PEC)

            - CONTROL STATIONS

            - LIGHT BEACONS / TOWER LAMPS

            - AUDIBLE WARNINGS

            - LLC / POWER DISTRIBUTION HARDWARE REQUIREMENTS

            - FIELD BUS COMMUNICATION

            - REQUIREMENTS FOR LICENSES

            - EMERGENCY STOP CONCEPT

            - BASIC CONVEYOR SYSTEM CONTROL FUNCTIONS

            - FUNCTIONAL DESIGN SPECIFICATIONS (FDS) SUBMITTAL

            - BHS CONTROL AND SCREENING ROOM

            - CONTROL PANEL POSITIONS

          - SUPERVISORY CONTROLS AND DATA ACQUISITION SYSTEM (SCADA)

          - SYSTEM TESTING AND HANDOVER

            - GENERAL

            - TEST BAGS

            - FACTORY ACCEPTANCE TESTS (FAT)

            - INSTALLATION TESTS AND SNAGGING

            - SITE ACCEPTANCE TESTS (SAT)

            - SETTLING DOWN

          - OPERATE AND MAINTENANCE (O&M) MANUALS

            - GENERAL

            - OPERATIONS MANUAL

            - MAINTENANCE MANUALS

          - TRAINING

            - GENERAL

            - TRAINING SCOPE

            - OPERATIONAL TRAINING

            - MAINTENANCE TRAINING

          - WARRANTY AND MAINTENANCE SERVICES

            - GENERAL

            - SUPPLIERS RESPONSIBILITIES

            - BUYER MAINTENANCE SERVICES

            - REQUIREMENTS FOR SUPPLY OF SPARE PARTS

            - SUPORT SERVICES

            - SUPPORT SERVICE SLA

            - PREVENTIVE MAINTENANCE SERVICES

            - SPECIAL WARRANTY

            - VIOLATIONS OF WARRANTY OBLIGATIONS

          - BHS AND XRAY SUPPLIER RESPONSIBILITY MATRIX

            - BHS INTEGRATION

            - IT INTEGRATION

          - BHS AND OTHER CONTRACTOR RESPONSIBILITY MATRIX

Technical supervision and quality assurance services for the implementation of the T5 Arrivals BHS project must include:

      - Evaluation of T5 arrivals BHS Suppliers documentation submitted during the project.

      - Attendance and evaluation of any key performance indicators during the Factory Acceptance Tests (FAT).

      - Expert consultations during the installation of the T5 arrivals BHS (the System layout, equipment selection and installation, integration management, other issues);

      - Witnessing and evaluation of launching of T5 arrivals BHS and acceptance testing (SAT). Revision of performed tests results and evaluation compliance with Technical specification requirements.

      - Witnessing and Evaluation of the T5 arrivals operational readiness tests;

      - Witnessing and evaluating of T5 arrivals BHS performance results during settling down period.

      - Other project technical support services necessary to ensure quality of the T5 arrivals BHS.

## Services Being Acquired

| No. | Name of the service | Maximum quantity | Service measurement name |
| --- | --- | --- | --- |
|  | Design services for Vilnius airport T5 arrivals BHS | 1 | Set |
|  | Technical supervision and quality assurance services for the implementation of the T5 Arrivals BHS project | 1 | Stage |
| - 2.1. | Technical support of the T5 arrivals BHS planning stage | 1 | Set |
| - 2.2. | Technical support of the production and the delivery stage of the T5 arrivals BHS | 1 | Set |
| - 2.3. | Technical support of the T5 arrivals BHS installation stage | 1 | Set |
| - 2.4. | Technical support of launching of the T5 arrivals BHS and Acceptance testing | 1 | Set |
| - 2.5. | Technical support of operational readiness. | 1 | Set |
| - 2.6. | Technical support of settling down period stage | 1 | Set |
|  | Additional consultation services as required (additional service hours dedicated to project change management) | 400 | Hours |

# GENERAL REQUIREMENTS FOR SERVICE PROVISION

## The BHS consultancy services Supplier or its experts will not be able out any other activities than defined in this document related to the implementation of the T5 arrivals BHS project (meaning the consultancy services of the BHS Installation Supplier or its subcontractors). If the Buyer determines that the Supplier or its experts engage in activities related with the Installation of the BHS projects, this agreement will be unilaterally terminated.

## The payment to the Supplier shall be made only after the provision of quality services.

## General requirements for the design of the T5 arrivals BHS at Vilnius Airport.

During the design phase, the Supplier must closely cooperate with the T5 Arrivals Terminal designer.

The Supplier shall undertake to ensure that the relevant results of the project shall comply with the legal acts and other requirements indicated in the Technical specification.

The supplier must evaluate the premises, buildings and surrounding areas of the BHS and based on the existing restrictions, offer the most effective solutions.

All design works must be done based on IATA recommendations and good practices at other airports.

A minimum of 5 baggage claim carousels must be designed (a maximum of 7).

BHS must be designed to handle at least 2,400 passengers with baggage in 1 hour.

A one-way traffic flow for baggage carts is considered in the baggage unloading area. A two-way flow may also be proposed if it can be properly integrated into the general airside traffic flow scheme near the terminal.

The Supplier will have to design baggage cart lanes with stopping bays on both sides. Next to the stopping bays, design baggage lines where luggage and other items are inspected via X-ray machines and transported to the baggage claim hall.

The space must ensure proper working conditions for baggage handlers and year-round protection of equipment.

There must be sufficient space between the line and the baggage cart stopping points for staff to unload baggage from the cart onto the line. The number of lines must match the number of carousels.

Incline-type carousels must be designed, with baggage delivered to them via a line located on an underground level.

An underground level will be designed beneath the entire carousel area. This level will house the necessary technical rooms and ensure the maintenance of the underground conveyors. The underground level must be planned in a way that allows for the installation of additional baggage lines in the second phase of the T5 implementation. The ceiling height of the rooms (to the structure) must be at least 3.7 meters (The height should be review with T5 terminal design team).

In the first phase, 5 incline-type baggage carousels will be installed, with a possibility to install 2 additional carousels in the second phase. Baggage will arrive at the centre of the carousel and be directed onto the rotating baggage claim belt. The spacing between adjacent carousels should allow enough space for passengers to wait and collect baggage without disrupting the flow of other passengers (ideally not less than 7 meters). The length of a single carousel may be 60–70 meters. See Annex No. 1 "Baggage Technology Scheme"; Carousel lengths must comply with IATA requirements. Terminal columns must be designed inside the carousel so that they do not interfere with passengers.

Supplier must design 1–2 lines for out-of-gauge (OOG) baggage retrieval. Sufficient space must be allocated near these lines for collecting large baggage without disrupting passenger flow.

The supplier must evaluate security measures: for passengers, maintenance staff, ground handling services, conveyor system, and other persons working in the BHS area.

The supplier must ensure compliance with all safety requirements, especially in those places where baggage is transported from the restricted access area to the critical access area.

The proposed BHS solution has to maximize the effective use of BHS's area.

The proposed BHS solution must leave maximum space for passengers. The designed system must provide comfortable access for passengers to the conveyor, comfortable movement of passengers in the baggage pick-up area, comfortable passengers waiting until the baggage is brought.

Maintenance simplicity must be considered, and enough space left to remove BHS failures.

## General requirements for the technical supervision and quality assurance services of the T5 Arrivals BHS implementation project.

T5 arrivals BHS Supplier is responsible for the implementation of the Project in a timely and appropriate quality. The Buyer will accept the results of the installation of the T5 arrivals BHS only after confirmation of Technical project support provider that the results are in accordance with the requirements specified in the Procurement Documents and the Analysis and Design Documentation and the recorded resolutions.

The Technical Support Supplier undertakes to control that the results of the project comply with the legal acts specified in the Technical Specification for the implementation of the System, as well as the technical and functional requirements described.

The Technical Support Supplier shall assess the quality of the services carried out in relation to the T5 arrivals BHS installation and the quality of the delivered equipment. The Technical Support Supplier shall evaluate the compliance of the equipment and the services with the technical requirements.

The Technical Support Supplier shall witness and evaluate the testing of the delivered equipment (participate in the acceptance testing).

The Technical Support Supplier shall consult the Buyer and the T5 arrivals BHS Supplier regarding all technical and project management issues related to the T5 arrivals BHS installation.

The Technical Support Supplier is obliged to attend meetings of the project. Remote participation is possible.

The Technical Support Supplier must submit reports on the Project result quality.

The Technical Support Supplier shall be responsible for the accommodation, transportation, working tools, means, and, if necessary, arrangement of the working premises for its employees (including all costs).

## General requirements for Additional consultation services as required.

The Buyer does not commit to order all the Services specified in the Contract.

BHS consultancy services will be ordered on demand for various BHS projects at Lithuanian airports. In each individual case, the amount of works and the preliminary price will have to be adjusted before the work is started.

# Requirement for the provision of the services

| ## No. | ## Scope of the services | ## Result of the services |
| --- | --- | --- |
| - T5 arrivals BHS design services. | The BHS layout must include: - BHS layout 2D and 3D BIM; - All parts of conveying system; - X-rays; - Baggage flow; - Security barriers; - Passenger movement flow; - Passenger waiting area; - Baggage loading positions for GH; - Baggage trolleys movement and parking positions; - The trajectories of the trolley's movement near the building and inside the building. - BHS control cabinets, electricity schemes, LAN schemes. - BHS CCTV layout. | - Detailed BHS layout in 2D .dwg format and 3D BIM model (more than one scheme can be provided). Electricity and LAN schemes in PDF or equivalent format. |
| - 2.1. Technical Project Support of the T5 arrivals BHS planning stage | During the stage the Technical Support Supplier shall: - Carry out the evaluation of the compliance of the technological and physical layouts submitted by the T5 arrivals BHS Supplier with the procurement documents. Submit the recommendations regarding the upgrading/optimisation of the technological and physical layouts. - Carry out the evaluation of the compliance of the documents submitted by the T5 arrivals BHS Supplier (the functional and logical architecture and technical design of the system) with the procurement documents. Provide recommendations for the content and the updating of the documents. - Provide a detailed plan for the provision of Project technical Support services. - Provide recommendations and agree with the detailed T5 arrivals BHS installation plan. - Provide the principles and the criteria for T5 arrivals BHS acceptance testing, - Submit the stage report. | - Evaluation of the compliance of the technical and physical layouts with the procurement documents and the upgrading recommendations. - Provision of evaluation of the T5 arrivals BHS design documentation, submission of the recommendations and the report. - Approval of the T5 arrivals BHS installation plan. - A plan for the provision of Project Technical Support services. - Acceptance testing criteria and principles. - Stage report. |
| - 2.2. The stage of production and the delivery of the T5 arrivals BHS | During the stage the Supplier shall: - Evaluate the compliance of the BHS with the procurement documents. - Participate in Factory Acceptance testing (FAT). | - Report on the evaluation of the compliance of the T5 arrivals BHS with the procurement documents. - FAT report. |
| - 2.3. The T5 arrivals BHS installation stage | During the stage the Supplier shall: - carry out a technical support of the services of the System Supplier; - Provide expert recommendations on the T5 arrivals BHS installation issues; - Evaluate the documents submitted by the T5 arrivals BHS Supplier. Submit proposals / recommendations regarding the content of the documents submitted by the T5 arrivals BHS Supplier; - Ensure the quality of the project results; - Test, inspect, and accept the equipment and the services submitted by the System Supplier. - Perform other activities provided in the project plan and the Project technical support services provision plan. - Submit the stage report. | - Reports of interim testing; - Reports on the compliance of the works performed and the delivered equipment; - Stage report. |
| 2.4. T5 arrivals BHS launching and acceptance testing stage | - During the stage the Supplier shall: - Carry out a technical support of the services of the T5 arrivals BHS Supplier; - Provide expert recommendations on the T5 arrivals BHS testing and commissioning issues; - Carry out the evaluation of the compliance of the services and the documents submitted by the T5 arrivals BHS Supplier with the procurement documents. - Evaluate the documents submitted by the T5 arrivals BHS Supplier. Submit proposals / recommendations regarding the content of the documents submitted by the T5 arrivals BHS Supplier; - Ensure the quality of the project results; - Evaluate whether the T5 arrivals BHS is suitable for use, it is installed in the appropriate volume and quality; - Participate in testing and verify equipment, software, integration and other services done by the T5 arrivals BHS Supplier. - Perform other activities provided in the project plan and the project technical support services provision plan. - Submit the stage report. | - Testing reports; - Reports on the compliance of the works performed and the delivered equipment with the procurement document; - Conclusion on the T5 arrivals BHS suitability for the commissioning and operation; - Stage report. |
| - 2.5. Operational readiness | - During the stage the Supplier shall: - Carry out a technical support of the services of the T5 arrivals BHS Supplier; - Evaluate the documents submitted by the T5 arrivals BHS Supplier. Submit proposals / recommendations regarding the content of the documents submitted by the T5 arrivals BHS Supplier; - Ensure the quality of the project results; - Perform other activities provided in the project plan and the project technical support services provision plan; - Submit the stage report. | - Stage report. |
| - 2.6. Settling down period stage | - During the stage the Supplier shall: - Carry out a technical support of the services of the T5 arrivals BHS Supplier; - Evaluate the documents submitted by the T5 arrivals BHS Supplier. Submit proposals / recommendations regarding the content of the documents submitted by the T5 arrivals BHS Supplier; - Ensure the quality of the project results; - Submit the stage report; - Perform other activities provided in the project plan and the project technical support services provision plan. | - Stage report. |

# Terms for the provision of the services

## Terms for the T5 Arrivals BHS design services.

The T5 arrivals BHS design work must be completed in 4 months after the order is placed.

Its possible to have technological break in T5 arrivals design stage due relation with T5 terminal design works. Exact work schedule must be agreed with the T5 Arrivals terminal design team.

## Terms for the technical supervision and quality assurance services of the T5 Arrivals BHS implementation project.

The stage reports shall be submitted within three days of the end of each stage.

The Technical Support Supplier shall submit the comments and recommendations for the documents submitted by the T5 arrivals BHS Supplier within 5 working days of the receipt of the documents. The Technical Support Supplier will respond within 3 working days to the comments submitted by the T5 arrivals BHS Supplier and / or the Buyer. Documents are matched with at least two iterations.

Other services specified in this document shall be carried out during the stages specified in the Technical specification of the T5 arrivals BHS installation. The services provided by the Technical Support Supplier shall not adversely affect the stages for the implementation of the project.

The T5 arrivals BHS testing and the quality assurance services shall be provided during the respective T5 arrivals BHS installation stages. The services provided by the Technical Support Supplier shall not affect the work of the T5 arrivals BHS Supplier or the terms (this statement does not apply to findings and recommendations of Technical Support Suppliers).

The terms of the service provision may vary depending on the simultaneously executed procurement of T5 arrivals BHS installation service. The Technical Support Supplier shall have to adjust to the terms indicated in the T5 arrivals BHS installation plan.

# NATIONAL, CYBER AND INFORMATION SECURITY REQUIREMENTS

## The Goods and Services offered by the Supplier must not pose a threat to national security. The Buyer, that manages the critical information infrastructure, shall have the right to consider that the Goods or Services offered by the Supplier pose a threat to national security when the Government of the Republic of Lithuania has adopted a decision confirming that the transaction, that is intended to be entered into, is not in the interests of national security in accordance with Article 13(11) of the Law on the Protection of Objects of Importance to Ensuring National Security. The manager of the critical information infrastructure (Buyer) will approach the Commission for the verification of the compliance of the transaction, that is intended to be entered into, with national security interests, and if the Commission will require the additional documents to be provided also by the other party to the transaction, that is intended to be entered into, then that other party will have to provide them.

## Suppliers and their subcontractors, which are not registered (are not permanently residing, if the Supplier or the subcontractor is a natural person) in the Member State of the European Union, in the Member State of the North Atlantic Treaty Organisation or in the third country which is a signatory to international agreements specified in Paragraph 4 of Article 29 of the Republic of Lithuania Law on Procurement by the entities, operating in the Field of Procurement, Waste Water Management, Energy, Transport or Postal Services, cannot participate in this Procurement.

## Buyer will manage the identified technological risks, that may arise during the performance of the Contract, in accordance with the procedure established by the Description of the Organizational and Technical Cyber Security Requirements Applicable to Cyber Security Entities, that was approved by the Resolution No 818 of the Government of the Republic of Lithuania of 13 August 2018.

## The Supplier shall undertake to comply with the provisions of the current version of the Republic of Lithuania Law on the Protection of Objects of Importance to Ensuring National Security https://e-seimas.lrs.lt/portal/legalAct/lt/TAD/TAIS.189498/asr

## The Service Provider, Contractor or Equipment Supplier shall undertake to ensure the compliance with the organizational and technical cyber security requirements, which are provided for in the Republic of Lithuania Law on Cyber Security, in the Resolution No 818 of the Government of the Republic of Lithuania of 13 August 2018 ‘On the Implementation of the Republic of Lithuania Law on Cyber Security‘, and in other legal acts.

## The Supplier shall undertake to comply, during the performance of the Contract, with the requirements of the internal information security and cyber security documents of the SE Lithuanian Airports. After signing the Contract, the Supplier will be made familiar, against signature, with the internal documents of the Enterprise that regulate security. The Supplier, respectively, also will be made familiar with the said documents upon the update thereof, and will undertake to comply with the requirements set out therein.

## In making a technical contribution in risk management of the technical elements of the BHS and EDS of the Project, the Supplier must monitor and evaluate whether the systems, that are being installed, meet the security requirements posed, and must prepare a risk management register and reports in accordance with Point 1 of the table in Chapter 3 of the Technical Specification.

## Buyer may inspect, during the performance of the Contract, if the Supplier complies with the requirements of the specified laws and internal documents.