## TECHNICAL SPECIFICATION

DESCRIPTION OF THE PROCUREMENT OBJECT

## TERMS

Buyer – AB LTG Cargo.

Supplier – economic operator – a natural person, a private legal entity, a public legal entity, other organizations and their subdivisions or a group of such persons with whom the Buyer concludes a Contract.

Goods – sets of lifting jacks for wagons.

Contract – a Contract concluded between the Supplier and the Buyer in respect of the Procurement object.

## PROCUREMENT OBJECT

  - Sets of lifting jacks for wagons (hereinafter referred to as the Procurement object).

  - The procurement object is not divided into lots.

  - Items and quantities of the procurement object:

| No. | PRODUCT NAME | UNIT OF MEASUREMENT | MAXIMUM QUANTITY* | MINIMUM QUANTITY OF GOODS TO BE REDEEMED |
| --- | --- | --- | --- | --- |
| 1. | Set of lifting jacks for wagons total capacity not less than 40 t | Pcs. | 11 | 6 |
| 2. | Set of lifting jacks for wagons total capacity not less than 20 t | Pcs. | 4 | 3 |
| 3. | Set of lifting jacks for wagons total capacity not less than 60 t | Pcs. | 2 | 2 |

* The specified maximum quantity is used only for the comparison of tenders, LTG Cargo will purchase the Procurement Object according to demand not exceeding the maximum quantity of the Goods.

## REQUIREMENTS FOR THE PROCUREMENT OBJECT

  - General requirements:

    - If the Technical Specification specifies a specific type, model, mark, applicable standard or other specific descriptive information of the purchased Goods, the Buyer shall accept an equivalent product that meets the parameters of the Goods specified in the Technical Specification and the applicable standards. The Supplier undertakes to submit/justify/prove equivalence to the object specified in the document.

When offering equivalent Goods, their properties may not be inferior (i.e. must be the same or better) than the requirements set forth in the procurement documents and the offered equivalent Goods may be used for their intended purpose without any restrictions (including, but not limited to):

- without making additional changes to the interoperable elements;

- the use will not affect faster wear and tear of the interacting elements, breakdowns and/or loss of warranty;

- the expected service life shall not be shorter;

- there is no inferior level of technical excellence.

    - The Goods must be new, unused, free from physical or functional defects.

    - The Goods (including their manufacturers) must not pose a threat to national security as specified in the Procurement Documents.

    - The Supplier must provide a warranty period for the Goods specified in the Supplier’s Tender (for which the economic efficiency scores are awarded) which cannot be shorter than 24 (twenty-four) months. The warranty period shall commence from the date of signing of the Goods Handover and Acceptance and Certificate.

  - The Goods must comply with the technical requirements set out in Annex No. 1 "Technical Specification (Special Part)" of this Technical specification.

FULFILMENT OF OBLIGATIONS

## PROCEDURE OF DELIVERY OF GOODS

  - The Contract shall be executed in the following stages and within the following time limits:

    - Stage I  - design.  The Supplier shall carry out the design process for the sets of lifting jacks for the wagons, during which all contractual requirements, including the requirements of Annex 2 to the Contract, "Technical Specification," shall be implemented in a specific and constructive manner. The result of the design process shall be a set of design documents for each item of procurement object. The Supplier shall submit the design documents to the Buyer in digital form for review and approval. The technical design of the sets of lifting jacks shall be approved by the Buyer no later than within 2 months after the entry into force of the Contract. The agreed technical design shall apply to all orders placed.

    - Stage II – production and factory acceptance at the Supplier's production facility after testing the Goods. Before shipping the Goods, the Supplier shall test the Goods at its production facility in the presence of the Buyer. During the testing, the Buyer shall check whether the Goods fully comply with all the requirements set out in Annex 2 to the Contract, "Technical Specification." The stage shall be considered complete when the Buyer signs the test report without any significant defects. The production and factory acceptance schedule must be agreed with the Buyer no later than within 30 (thirty) calendar days from the date of submission of the order. The schedule may be amended by mutual written agreement between the Buyer and the Supplier. Tests shall be performed for each Good, unless the Buyer and the Supplier agree otherwise in writing.

    - Stage III – delivery. Delivery shall be made to the specific address indicated by the Buyer during the Buyer's business hours (Monday to Friday, 8:00 a.m. to 5:00 p.m.). The place of delivery of the Goods is Puškino str. 1, Radviliškis. The Goods must be delivered no later than within 12 (twelve) months from the date of placing the order (long-term contract, multiple orders). A set of spare parts and consumables sufficient for technical maintenance and ensuring the proper technical condition of the Goods during the period specified in the Supplier's Tender (for which economic efficiency scores are awarded) must be delivered together with the Goods.   The stage is considered complete when the Buyer confirms in writing the delivery of the Goods to the place of delivery.  The delivery schedule of the Goods must be agreed with the Buyer no later than within 15 (fifteen) calendar days from the end of Stage II. The schedule may be amended by mutual written agreement between the Buyer and the Supplier.

    - Stage IV – Installation, commissioning, calibration and testing under the supervision of the Supplier.  The stage shall be considered complete when the Buyer signs the final Goods transfer and acceptance certificate.  The schedule for installation, commissioning, calibration, and testing must be agreed with the Buyer no later than within 15 (fifteen) calendar days from the end of Stage III. The schedule may be amended by mutual written agreement between the Buyer and the Supplier.

  - The orders shall be placed by     Email  specified by the Supplier and shall be deemed received immediately on the day the order is placed.

  - The minimum order size is the minimum quantity of Goods to be purchased specified in clause 2.3 of the Technical Specification.

  - Transportation, loading, unloading, installation, commissioning, calibration and testing of the Goods will be carried out at the Supplier's expense, these costs must be included in the price of the Tender.

  - During the performance of the Contract, the Supplier shall not be entitled to supply Goods that do not comply with the requirements of the Procurement Documents and/or the supply of which is restricted due to international sanctions (within the meaning of the Law on International Sanctions of the Republic of Lithuania) and/or due to their threat to national security, as defined in the Procurement Documents and in the Law on Procurement of the Republic of Lithuania by Contracting Entities in the Field of Water Management, Energy, Transport and Postal Services.

  - The Supplier must inform the Buyer in writing (by e-mail) about the country of origin of the ordered Goods and the manufacturer of the Goods (its name, enterprise legal code, country of registration) not later than within 5 (five) business days from the receipt of the order, prior to the execution of the order. The provision of this information shall be included in the time limit for the execution of the order.

## PROCEDURE AND DEADLINES FOR RECTIFICATION OF DEFECTS

  - Defects in the Goods identified at the time of acceptance of the Goods must be eliminated no later than within 15 (fifteen) calendar days from the date of sending the Buyer's notification by e-mail (unless the Parties agree otherwise in writing).

  - If the last day of the term for the delivery of the Goods or the elimination of defects of the Goods falls on a non-business day or public holiday, the day of expiry of the term shall be considered the business day following it. Public holidays and non-business days (Saturdays and Sundays) are included in the deadline for delivery of the Goods or elimination of defects of the Goods.

ACCESSORIES

Annex 1 – Technical specification (special part);

Annex 2 – Environmental (green) criteria.