Task designer training services

1. GENERAL INFORMATION

1.1. Contracting authority: National Education Agency (hereinafter referred to as the Contracting Authority). Address: K. Kalinausko g. 7, LT-03107 Vilnius.

1.2. General information about the context of the procurement:

Project "Strengthening the assessment of learning outcomes and progress", No. 10-062-P-0001 (hereinafter referred to as the project) complies with the progress measure 12-003-03-01-03 "Ensuring modern educational content accessible to all" of the 2021-2030 development programme of the Ministry of Education, Science and Sport of the Republic of Lithuania. The project is designed to address the problems detailed and described in progress measure 12-003-03-01-03 "Ensuring modern educational content accessible to all": uneven quality of education and a fragmented system for ensuring it have a negative impact on pupils' learning outcomes, and there is a lack of modern education that meets pupils' needs and of assessment of their achievements and progress. The project activities will aim to achieve the indicators set out in the progress measure.

In order to obtain a secondary education, a student completing a secondary education programme and seeking to obtain a document certifying this – a school leaving certificate – must pass state school leaving examinations (hereinafter referred to as SLE). According to the legislation currently in force, they must pass at least two: the compulsory Lithuanian language and literature (A, B) and one optional VBE. The mathematics (A, B) VBE is compulsory for those who wish to study in higher education programmes in state-funded places, as the VBE results are used for admission to higher education programmes.

1.3. The purpose of the procurement is to purchase training services for experts who prepare external student achievement assessment tools (summative assessment tasks, assessment criteria). The purpose of this training is to improve the qualifications of developers of external summary assessment tools for student achievement and specialists working at the contracting authority (National Education Agency) and supervising the preparation of VBE tasks, with a view to improving the external summary assessment system for student achievement and ensuring that uniform task preparation principles, known and understood by users, are applied.

1.4. The target group for the training is teaching staff, developers of external summary assessment tools for student achievement and specialists working for the contracting authority, as well as other specialists in the education system (hereinafter referred to as participants).

2. PURCHASE OBJECT

2.1. The object of the procurement is the preparation of training programmes and training materials and the provision of lecturer services.

2.2. The procurement is not divided into parts. The procurement is not divided into parts because the services being procured are integrated; the parts of the services (training programme, training materials and training based on the prepared materials) are closely related. The non-division of the purchase is justified by the need to purchase high-quality services in a rational and effective manner (it is expected that the lecturers will not only present the training materials, but will also have to evaluate the tasks prepared by the learners and provide consultation).

2.3. It is expected that the training will be aimed at three types of participants:

2.3.1. Beginner training participants (TDN) – participants who have never prepared a VBE task or sample and have not participated in any external summary assessment training on VBE statistics and task preparation;

2.3.2. Advanced training participants (TDE) are participants who have participated in external summary assessment training on VBE statistics and task preparation or have prepared at least one VBE task or sample.

2.3.3. Task preparation coordinators (CM) are employees of the contracting authority (NŠA).

2.4. The Contracting Authority will select the participants and assign them to participant types. The list of participants will be provided to the service provider at least 10 days before the start of the training.

2.5. It is expected that the training will take place in sessions according to the approved schedule:

2.5.1. Introductory training will be provided to all training participants (TDN, TDE, CM). The scope of the introductory training is 16 academic hours. The first 8 academic hours will be conducted continuously in a contact manner, with the participation of TDN, TDE and CM. The remaining 8 academic hours will be conducted with the participants divided as follows: 4 academic hours will be conducted remotely with TDN, TDE and CM participating, 4 academic hours will be conducted remotely with TDN and TDE participating together, and CM will work separately in a contact manner during these 4 academic hours.

2.5.2. Special training according to participant types will be conducted remotely.

2.6. It is expected that some of the training sessions will be conducted by combining different types of participants according to common training topics. The structure, duration and number of participants in the sessions are presented in Table 1.

2.7. Training participants are divided into groups. A training group may consist of no more than 23 participants. During the training, participants may be divided into chat rooms as needed. Participants in contact-based classes study at the premises of the Contracting Authority.

Preliminary training structure, number of training groups

Table 1

| No. No | Training participants | Training duration (academic hours) | Number of training groups | Type of training | Comments |
| --- | --- | --- | --- | --- | --- |
| Introductory training |  |  |  |  |  |
| 1. | Beginners (TDN), advanced learners (TDE) and task coordinators (CM). Task preparation coordinators (CM) | 16 academic hours | Contact: 2 groups Distance learning: 1 group | Contact and distance | When training is conducted remotely, it begins no earlier than 3 p.m. and ends no later than 7 p.m. |
| Special training according to participant types |  |  |  |  |  |
| 2 | Beginners (TDN) | 16 academic hours | 4 groups | Remote | Training shall commence no earlier than 2 p.m. and end no later than 6 p.m. |
| 3. | Beginners and advanced learners (TDN and TDE) | 8 academic hours | 4 groups | Remote |  |
| 4 | Advanced (TDE) | 8 academic hours | 4 groups | Remote |  |
| 5. | Advanced (TDE) and task preparation coordinators (CM) | 8 academic hours | 4 groups | Remote |  |
| 6 | Task preparation coordinators (CM) | 16 academic hours | Group 1 | Remote |  |

3. PURPOSE OF THE SERVICES TO BE PURCHASED

3.1. Services for the preparation of TDN, TDE and CM training programmes and training materials (40 academic hours, 3 types of participants in total) and training in accordance with the prepared training programme parts (mixed training (lecturer services) in accordance with the scope specified in Table 1). The training programme must be prepared in Lithuanian or English;

3.2. Provision of training services in accordance with the training programme.

4. GENERAL REQUIREMENTS FOR THE IMPLEMENTATION OF SERVICES

4.1. Prepare a 40-hour training programme, which is tailored to the 3 types of participants, with training materials (hereinafter referred to as the Programme). Implement training for TDN, TDE and CM in accordance with the prepared Programme. Classes for TDN and TDE separately and for TDN and TDE together are divided into 4 subject groups (e.g. social studies, natural sciences, etc.).

4.2. The total training volume is 40 academic hours per target group, including 10 academic hours for self-study.

4.3. Training shall be conducted in a blended manner:

4.3.1. The introductory 16 academic hours of training must be conducted in accordance with the conditions set out in points 2.5.1 and 2.6;

4.3.2. Remote training shall be conducted using video conferencing software provided by the Contracting Authority;

4.3.3. For training organised in person, the Contracting Authority shall provide training facilities with a computer for the lecturer, a screen and a projector. The Provider shall provide handouts for the participants.

4.4. The price of the training must include all costs related to the implementation of the training, the preparation of training materials, training materials for participants, lecturer preparation, evaluation of training participants' work, lecturer travel expenses, accommodation and daily allowances.

5.  REQUIREMENTS FOR THE PROGRAMME AND TRAINING MATERIALS

5.1. General requirements for the programme.

5.1.1. The programme must consist of the following parts:

5.1.1.1. an abstract briefly describing the essence, purpose, relevance and benefits of the programme for the target group, a reasonable distribution of the number of hours in the programme, and an objective defining the programme as a whole and indicating the direction of its implementation;

5.1.1.2. Programme content – a prerequisite and means for achieving the set objective. The content must reflect the consistency and comprehensiveness of the implementation of activities (topics) and the reasonableness of the time allocation (indicating the time allocated to each topic). Time must be set aside for reflection (reporting, evaluation and self-assessment).

5.1.1.3. Competences that will be acquired/developed by programme participants. Competence – the totality of a person's knowledge, skills, abilities, attitudes and values demonstrated in a specific activity.

5.1.2. The Programme must describe the planned active teaching (learning) methods, practical activity application methods and/or techniques. At least 40 per cent of the Programme must be focused on practical activities.

5.1.3. The language of the prepared Programme and programme materials must be correct, and the programme and materials must be prepared in Lithuanian or English.

5.1.4. The Programme must be prepared in accordance with the "Procedures for the Evaluation of Qualification Improvement Programmes and the Issuance of Qualification Improvement Certificates", approved by Order No. VK-480 of the Director of the National Education Agency on 24 August 2020. "Procedures for the Evaluation of Qualification Improvement Programmes and the Issuance of Qualification Improvement Certificates" (available online at xml-ph-0000@dee.lt). "On the Procedure for the Evaluation of Qualification Improvement Programmes and the Issuance of Qualification Improvement Certificates" (available online atwww.nsa.smm.lt/wp-content/uploads/2020/10/programu-ir-pazymejimu-aprasas.pdf ). The programme must be submitted by completing Appendix 1.

5.1.5. The service provider is responsible for the copyright of the text, video and audio material used. The approved Order No. V-755 of the Minister of Education, Science and Sport of the Republic of Lithuania of 26 June 2019 (as amended by Order No. V-836 of the Minister of Education, Science and Sport of the Republic of Lithuania of 25 May 2022). When providing services, the Service Provider shall be responsible for the visual, textual and audio material, designs, patents, trade names, trademarks and labels, program code, computers and software, interfaces, other copyrighted, related or industrial property rights, the supplier shall be responsible for obtaining the relevant rights, necessary permits, licences and other necessary rights. The contracting authority may require the supplier to provide evidence of the necessary permits, licences and other rights required for the provision of the Services and/or the use of the created works.

5.2. Requirements for the content of the Programme.

5.2.1. The training programme must cover the following main topics (stages of task preparation):

5.2.1.1. setting general provisions for achievement checks and assessment objectives;

5.2.1.2. preparation of the structure of achievement assessment tasks and question specifications;

5.2.1.3. creation of questions that make up the achievement assessment task;

5.2.1.4. Pre-testing of the questions that make up the achievement assessment task;

5.2.1.5. Quality assessment of the questions that make up the achievement assessment task and their adjustment after testing;

5.2.1.6. Designing achievement assessment tasks using classical and modern psychometric methods;

5.2.1.7. Evaluation of the quality of constructed achievement assessment tasks after actual testing;

5.2.1.8. Interpretation of achievement assessment results, justification of task quality, and provision of recommendations and corrective actions for other task development cycles.

5.2.2 The programme must be designed for three types of participants:

5.2.2.1. TDN participants. The first six topics listed in point 5.2.1 must be presented in detail to TDN participants. The first three topics should give training participants a general understanding of task development, and training participants should also be familiarised with the task testing process and how to evaluate each question or task based on the test results. The psychometric principles of task quality assessment must also be presented so that training participants can read, understand and interpret the psychometric parameters of questions obtained during test testing. The TDN must present the basic principles of task construction and task quality assessment based on statistical analysis. The principles of assessment instructions and metadata compilation must also be presented. Training participants will have to prepare tasks according to the agreed task preparation model, which will be checked by lecturers and commented on.

TDN will participate in the initial training together with all training participants (see Table 1, No. 1; 16 academic hours). Subsequent training sessions should be dedicated solely to TDN (see Table 1, No. 2; 16 academic hours), while the final training seminars should be organised together with TDE (see Table 1, No. 3; 8 academic hours).

5.2.2.2. TDE participants. The first six topics listed in section 5.2.1 must be presented to the TDE. The TDE will additionally delve into the psychometric principles of task assessment in order to understand and interpret the data obtained during test trials. This group will delve into the principles of task construction, learn to evaluate the quality of questions that make up the tasks based on psychometric analysis, learn to identify errors in questions and find solutions for correcting them, and become familiar with the principles of creating assessment instructions and metadata.

TDE will participate in initial training together with all training participants (see Table 1, No. 1), then joint sessions with TDN must be organised for them (see Table 1, No. 3; 8 academic hours). In the next stage, which covers more complex topics specific to TDE, two training sessions of 4 academic hours each must be organised (see Table 1, No. 4; 8 academic hours). TDE will also participate in two sessions together with CM (see Table 1, No. 5; 8 academic hours). Training participants will have to prepare tasks according to the agreed task preparation model, which will be checked by lecturers and commented on.

5.2.2.3. CM participants. CM training must cover all 8 stages of task preparation (see point 5.2.1). CM, together with all participants, must participate in the initial training (see Table 1, No. 1; 12 hours) and a separate contact training session dedicated to CM, which should be focused on clarifying the role of CM, reviewing the entire task preparation cycle and mastering the task preparation coordination process.

In subsequent training sessions, CMs must learn to evaluate the quality of the material provided by the authors of the tasks, determine whether the questions and answers prepared by the authors of the tasks fully comply with the latest subject knowledge and international standards, and evaluate the structure and suitability of the tasks. CMs must evaluate each task and block of tasks and ensure that they meet the quality requirements, confidentiality and security.

CM will participate in joint sessions with TDE training participants (see Table 1, No. 5; 8 academic hours) and in separate training sessions intended only for CM (see Table 1, No. 6; 16 hours).

When presenting psychometric analyses and assessments in training, a specialist practitioner must be present who participates in the assessment of the prepared task questions and is able to present the most common mistakes in practice.

5.3. Requirements for training materials prepared in conjunction with the Programme.

5.3.1. The training material must correspond to the specifics of the Programme for which it is being prepared and be prepared in Lithuanian or English.

5.3.2. Modern and classical test theories, their concepts and interpretations shall be presented; their structure shall be consistent, corresponding to the content topics, applicable and understandable to the target group, and their language shall be correct. The training material must have lasting value, be applicable in practice (recommendations for the application of the training material must be provided), and its scope must correspond to the scope of the prepared Programme. When conducting training remotely, it is mandatory to provide participants with the training material in the chosen form (at least one of the following forms: Power Point TM , Word, PDF, audio, video material).

5.3.3. Suggested structure for the training materials: title page, contents (according to the Programme topics), introduction, structured presentation, recommendations for application, appendices (if any), list of recommended literature and sources used.

5.3.4. The teaching materials must not infringe the rights of other authors.

6. ADDITIONAL REQUIREMENTS

6.1. Requirements for the submission of the Programme with training materials.

6.1.1. After the contract with the Contracting Authority comes into force, a Programme for three types of participants shall be prepared within 20 working days and submitted to the Contracting Authority for evaluation at .

6.1.2. The Programme shall be evaluated within 10 working days of submission and submitted to the Supplier for correction (if there are any comments).

6.1.3. The Programme shall be revised in accordance with the comments received within 5 working days of receipt of the comments on the Programme from the Contracting Authority. If the Contracting Authority submits additional comments on the final version of the Programme, it shall be revised again.

6.1.4. The training materials for the Programme, designed for three types of participants, shall be prepared and submitted to the Contracting Authority within 20 working days of the Programme's approval.

6.1.5. The training materials for the Programme shall be evaluated within 10 working days and submitted to the Supplier for revision (if there are any comments).

6.1.6. The programme material shall be revised in accordance with the evaluation comments within 10 working days of receipt of the comments from the Contracting Authority. If the Contracting Authority submits additional comments on the final version of the programme material, it shall be revised again.

6.1.7. The programme with the training material shall be submitted to the Contracting Authority by e-mail, and if the training material consists of large files that cannot be sent by e-mail, they shall be submitted on a digital medium (USB memory stick) or by means designed for sending large files.

7. PROGRAMME IMPLEMENTATION REQUIREMENTS

7.1. General requirements for programme implementation.

7.1.1. Within 10 working days of the Programme's approval, the Provider must arrange a meeting with the Contracting Authority and submit and agree on a draft training schedule with the Contracting Authority. The training schedule may be changed due to unforeseen circumstances at the initiative of the Contracting Authority, subject to separate agreement with the Service Provider no later than 2 working days before the training date.

7.1.2. Upon completion of all training courses under the Programme, the Provider shall issue a certificate to each participant who has completed the training programme (including practical tasks). Certificates shall be issued to training participants who have attended at least 80% of the training.

7.1.3. During and after the training, the Contracting Authority will collect feedback from training participants on the quality of the training.

7.1.4. The Provider must appoint a responsible person (or persons) whom the Contracting Authority could contact regarding the services provided or payments, as well as in the event of problems arising during the implementation of the training.

7.1.5. All documentation (the Programme, training materials, document forms, publicity materials, certificates for participants) must feature publicity marks and the name of the project implemented by the Contracting Authority – "Strengthening the assessment of learning outcomes and progress", the following mandatory publicity marks must be used: the emblem of the European Union with the statement: "Funded by the European Union" (hereinafter referred to as the mark), the OP logo, available on the website https://www.nsa.smm.lt/about-nsa/nsa-logo/, the logo of the Ministry of Education, Science and Sport of the Republic of Lithuania, available on the website https://smsm.lrv.lt/lt/administracine-informacija/ministerijos-logotipas.

7.1.6. Where possible, aspects of equal opportunities and gender equality must be included in the content of the activities.

7.1.7. When developing the content of training programmes and other products, they must be organised and developed in accordance with the principles of universal design and innovation (creativity) (e.g. accessibility, flexibility, simple and intuitive use, tolerance to errors, etc.).

7.2. Training delivery requirements.

7.2.1. The content, methods and competencies provided in the training must correspond to the specifics of the prepared Programme. Between theoretical training sessions, participants must perform practical tasks at their workplaces, and lecturers must consult and comment on/evaluate the tasks performed.

7.2.2. Participants must be given the opportunity to participate in group work in chat rooms.

7.2.3. No later than 3 days before the training, the provider must share the agenda for the specific part of the training with the contracting authority, which the contracting authority will send to the training participants.

7.2.4. The Contracting Authority will make video recordings of the remote training. The video recordings will be available to training participants for no longer than one month after the training.

7.2.5. The Contracting Authority shall be responsible for selecting the remote learning environment, inviting training participants (the list of participants shall be provided by the Contracting Authority) and registering participants who connect remotely during the training.

7.2.6. Only the lecturers and specialists specified in the tender submitted by the Supplier may conduct the training and prepare the training programme and training materials. In justified circumstances, subject to written agreement with the Contracting Authority, the lecturer(s)/specialist(s) may be replaced by another lecturer(s)/specialist(s) of no lower qualification.

7.2.7. Training may be conducted in Lithuanian or English.

7.3. Requirements for the formation of training groups and invitations to training.

7.3.1. Groups shall be formed by the Contracting Authority. The Contracting Authority shall provide the Supplier with a preliminary list of training participants no later than 10 working days before the start of the training.

7.3.2. The Contracting Authority shall register participants for specific training and share the list of participants with the Provider.

7.4. Requirements for participant registration.

7.4.1. The Contracting Authority shall be responsible for registering training participants at the start of the training, on each day of the training.

7.5.  Terms of service provision.

7.5.1. All services must be provided in accordance with the agreed schedule within 32 (thirty-two) months from the date of entry into force of the service purchase contract with the Contracting Authority. The indicative deadlines for the stages of service provision may be adjusted in writing with the consent of the Contracting Authority:

| Technical specifications point | Description of the part of the procurement object | Preliminary deadlines |
| --- | --- | --- |
| 7.1.1 | A remote meeting with the Contracting Authority has been held and a training schedule has been agreed. | Within 10 working days of the Programme's approval, the Supplier must hold a meeting with the Contracting Authority and submit and agree on a draft training schedule with the Contracting Authority. The training schedule may be changed due to unforeseen circumstances at the initiative of the Contracting Authority, subject to separate agreement with the Service Provider no later than 2 working days before the training date. |
| 6.1.1 | The Programme has been prepared. | After the contract with the Contracting Authority enters into force, the Programme for three types of participants shall be prepared within 20 working days and submitted to the Contracting Authority for evaluation. |
| 6.1.2 | Evaluated Programme. | The Programme shall be evaluated within 10 working days of submission and submitted to the Supplier for correction (if there are any comments). |
| 6.1.3 | Programme adjusted according to the evaluation comments. | The Programme shall be revised in accordance with the evaluation comments within 5 working days of receipt of the comments on the Programme from the Contracting Authority. If the Contracting Authority submits additional comments on the final version of the Programme, it shall be revised again. |
| 6.1.4 | Programme materials prepared. | The training materials for the Programme, designed for three types of participants, shall be prepared and submitted to the Contracting Authority within 20 working days of the Programme's approval. |
| 6.1.5. | Programme materials evaluated. | The Programme training materials shall be evaluated within 10 working days and submitted to the Supplier for correction (if there are any comments). |
| 6.1.6 | Programme materials revised in accordance with the evaluation comments. | The programme material shall be amended in accordance with the evaluation comments within 10 working days of receipt of the comments from the contracting authority. If the contracting authority submits additional comments on the final version of the programme material, it shall be amended again. |
| 7.2.3. | The agenda for a specific part of the training has been submitted. | No later than 3 days before the training, the provider shall share the agenda for the specific part of the training with the Contracting Authority, which the Contracting Authority shall send to the training participants. |
| 7.5 | Terms of service provision. | All services must be provided in accordance with the agreed schedule within 32 (thirty-two) months from the date of entry into force of the service purchase contract with the Contracting Authority. The indicative deadlines for the stages of the services may be adjusted in writing with the consent of the Contracting Authority. |

7.5.2. Procedure for submitting results: the results of each point shall be submitted to the person specified in the project contract who is responsible for the performance of the contract.

7.5.3. The Supplier shall be paid in instalments: after the Supplier has prepared the Programme and the Programme materials (sub-points 6.1.1 – 6.1.6 ) and the Contracting Authority has confirmed the performance of these services; performance shall be confirmed by the Parties signing the Service Delivery and Acceptance Act. The remaining value of the Contract shall be paid for each training group that has been paid for and after the Contracting Authority has confirmed the performance of the training; performance shall be confirmed by the Parties signing the Service Transfer-Acceptance Act.

7.5.4. Deviations from the service deadlines specified in sub-clauses 6.1.1 and 6.1.4 (in total) may not exceed 1 week. The service provision schedule may be adjusted at the initiative of the Purchaser during the course of the work.

- ENVIRONMENTAL PROTECTION (GREEN) REQUIREMENTS

8.1. In accordance with Order No. D1-508 of the Minister of the Environment of the Republic of Lithuania of 28 June 2011 (2022-12-13 No. D1- 401, current version) "On the approval of the procedure for the application of environmental protection criteria in green procurement", the subject of the procurement meets the condition set out in point 4.4.3 of the Procedure, i.e. the service being purchased is of an intangible (intellectual) nature, is not related to the creation of a tangible object, and its supply is not expected to have a significant negative impact on the environment, create a source of pollution or generate waste[1] , therefore, the object of the purchase meets this requirement.

___________________