(Draft)

CONSTRUCTION CONTRACT SALE AND PURCHASE AGREEMENT NO.

___ ___________ 20

Klaipėda

Joint Stock Company Klaipėda State Seaport Authority, legal entity code 240329870, registered office address J. Janonio g. 24-1, 92251 Klaipėda, the data on the company being collected and stored in the Register of Legal Entities of the Republic of Lithuania, represented by the CEO Algis Latakas, acting in accordance with the company’s Articles of Association, hereinafter - the Customer,

and

.................................... represented by .................................., acting on the basis of [Articles of Association], hereinafter - the Contractor, hereinafter in this Construction Works Purchase and Sale Contract collectively referred to as the Parties and individually - the Party, have entered into this Construction Works Purchase and Sale Contract (hereinafter - the Contract), and have agreed on the following terms and conditions.

1. SUBJECT MATTER OF THE CONTRACT

1.1. The Contractor undertakes to carry out, on its own risk, with its own materials, equipment (hereinafter - the Materials) and funds, the construction (hereinafter - the Works) of the object "Transport communication structures (southern and northern dams, piers, and quays) constraction at Kairių st. 17, Klaipėda“ construction stage I (hereinafter - the Object), in accordance with the technical design (hereinafter - the Design) provided by the Customer and to hand over the Works to the Customer, and the Customer undertakes to accept and pay for the Works in accordance with the procedure set out in the Contract. The Works shall be scheduled so that the northern dam (Part 1) is built first, followed by the southern dam.

# 2. CONTRACT VALIDITY, TERMS OF PERFORMANCE

2.1. The Contract shall enter into force upon its signature by both Parties and upon submission by the Contractor of a performance security in accordance with the terms and conditions of the Contract. The Contract shall remain in force until the obligations under the Contract have been fully discharged.

2.2. The total time for completion of the Works shall be 750 (seven hundred and fifty) days. The total time for completion of the Works shall include:

2.2.1 the handover of the technical design and the construction permit (hereinafter - the SLD) to the Contractor - within 10 days from the date of entry into force of the Contract;

2.2.2. handover of the construction site to the Contractor within 20 (twenty) days after the conditions in subparagraph 2.2.1 have been fulfilled;

2.2.3. completion of the Works and handing over of the completed Works to the Customer with the mandatory construction completion documents - within 660 (six hundred and sixty) days from the conditions fulfilled in subparagraph 2.2.2;

2.2.4. Construction completion procedures - within 60 (sixty) days of receipt from the Contractor of all the mandatory completion documents specified in subparagraph 2.2.3 of the Contract.

2.3. The process and sequence of performance of the Works shall be determined in accordance with the calendar schedule for the performance of the Works drawn up by the Contractor and agreed according to the procedure laid down in the Contract.

2.4. If during the performance of the Contract the circumstances provided for in paragraph 2.6 of the Contract or other circumstances not provided for in the Contract transpire which the Contractor could not reasonably have foreseen, the time limit for the completion of the Works may, by agreement between the Parties, may be extended for the duration of the circumstances preventing the timely completion of the Works.

2.5. A request for an extension of the time limit for the performance of the Works, together with all documents supporting the request, must be submitted to the Customer before the expiry of the time limit for the performance of the Works requested for extension. Extension of the time limit for performance of the Works shall be agreed in writing between the Customer and the Contractor.

2.6. The Contractor shall have the right to apply to the Customer for an extension of the time limit for performance of the Works if:

2.6.1. the Customer fails to perform or improperly performs its obligations under the Contract and, as a result, the Contractor is unable to carry out the Works in part or in full;

2.6.2. the instructions given by the Customer to the Contractor shall affect the Contractor’s time for the completion of the Works;

2.6.3. the meteorological conditions are exceptionally unfavourable for the execution of the technological process (the works may not be carried out if they do not comply with the requirements of the normative documents), i.e. for floating or crane works, the maximum wind speed at 10 metres is equal to or greater than 15 m/s when such conditions last for more than 3 hours. during working hours (certificate from the Meteorological Office), air temperature below -15 °C (certificate from the Meteorological Office), ice drift, visibility due to fog of less than 0,8 km, wave height at sea of more than 1,50 m (for dredgers dumping at sea) (certificate from the Meteorological Office), for other works, the air temperature is below -10 °C and the ground temperature is below -5 °C (certificate from the Meteorological Office), and where the information provided by the Contractor has been confirmed by the person carrying out the the technical supervision;

2.6.4. any delay, hindrance or obstruction caused by or attributable to the Customer and/or third parties employed by the Customer, or acts of third parties outside the Customer’s control, which prevent the Contractor from completing the Works on time;

2.6.5. the need for additional works arises when performing the Contract and their performance affects the time limit for the completion of the Works;

2.6.6. provisions of legal acts of the Republic of Lithuania governing the duration, time limits and/or the procedure of acceptance of the Works change during performance of the Contract.

3. PRICE (PRICING RULES) AND PAYMENT TERMS

3.1. The method used to calculate the Contract price shall be the fixed price.

3.2. Contract Price:

| Contract Price excluding VAT | ______________ (indicate the amount in figures and the currency of payment) |
| --- | --- |
| VAT (21 %) | ______________ (specify amount in figures and currency of payment) |
| Contract price (sum of Contract price excluding VAT and VAT) | ______________ (specify the amount in figures and currency of payment) |

3.3. The initial value of the Contract shall be equal to the Contract price without VAT as indicated at the time of conclusion of the Contract, i.e. EUR ________. The initial value of the Contract shall remain unchanged throughout the Contract term, unless the Contract Price is revised according to the procedure set out in the Contract due to a change in the price level.

3.4. The Contract Price shall include all costs incurred by the Contractor in connection with the proper performance of its obligations under the Contract and all taxes, including Value Added Tax (hereinafter - VAT). VAT shall be paid according to mandatory regulatory acts, applicable laws of the Republic of Lithuania and international agreements.

3.5. The Contractor shall, at their own expense, fulfil all tax obligations and (or levies) which arise or may arise during the performance of the Contract and shall bear all risks associated with the payment of such tax obligations and/or levies, if any. The Customer shall not reimburse the Contractor for any costs incurred by the latter in connection with the proper performance of the obligations referred to in this paragraph, except in the other cases, if any, set out in the Contract.

3.6. The Customer shall pay the Contractor the Contract Price for the entire object of the Contract provided for in the Contract, provided that the actual quantity of the Works does not vary by more than 10 (ten) per cent from the original Contract Value.

3.7. The Contract Price shall remain unchanged throughout the term of the Contract, except in the case of price review and modification provided for in the Contract:

3.7.1. due to changes in taxes - if during the term of the Contract VAT applicable to the Works changes, the Contract will be subject to the revised VAT rate. The Contract price shall be revised after the date of entry into force of the Law of the Republic of Lithuania on Value Added Tax amending the rate of the tax. The Contract price excluding VAT will not be revised as a result of the tax change, unless otherwise provided by the adopted legal acts. The Contract Price recalculated as a result of a change in VAT will be equal to the amount obtained by adding VAT calculated at the newly adopted tax rate to the Contract Price, excluding VAT, unless otherwise provided by adopted legal acts.. The Contract Price shall be recalculated for the Works that are performed and paid for under the Contract after the entry into force of the relevant legal act;

3.7.2. due to the price level change - the Contract Price may be recalculated, on the initiative of the Party concerned and on the basis of the documents submitted by the Party concerned, due to a change in the price index for the construction of administrative buildings published by the State Data Agency [the Construction Cost Price Index for the construction of administrative buildings, as published by the Department of Statistics] (hereinafter - the Index), if the Index changes of more than 10 (ten) percent. The recalculation shall be carried out in accordance with established procedure:

3.7.2.1. The time of the revision shall be the date of receipt of the Party’s request to the other Party to revise the Contract Price.

3.7.2.2. The first review of the Contract Price may take place not earlier than 12 (twelve) months after the date of entry into force of the Contract and subsequently the Contract Price may be revised not more frequently than every 12 (twelve) months from the time of the last review.

3.7.2.3. The Contract Price shall be recalculated by multiplying the value of the construction works not handed over to the Customer under the Contract by the Index Change Factor, calculated in accordance with the formula:

K = In / Ipr

Where:

K - coefficient of change of the Index;

In – the value of the Index in the month of the review (the date of receipt of the request for review of the Contract Price by the other Party);

Ipr – the value of the Index at the beginning of the review period; in the case of the first revision, the beginning of the period (month) shall be the month of the date of entry into force of the Contract. For the second and subsequent revisions, the beginning of the period (month) shall be the month of the published value of the Index used at the time of the last revision.

3.7.2.4. For the calculation of the coefficient of the Index, the Index values shall be taken at the accuracy of 4 (four) decimal places and the resulting value of the coefficient of the Index shall be rounded off to 2 (two) decimal places, with the last digit increased by one if the first digit following it is between 5 and 9

3.7.2.5. If the resulting coefficient (K) of the Index is greater than 1.10 (one and one tenth), the revised Contract price shall be increased by multiplying it by the resulting coefficient, and if the resulting coefficient is less than 0.90 (ninety hundredths), the revised Contract Price shall be reduced by multiplying it by the resulting coefficient.

3.7.2.6. Only the part of the Contract price of the construction works not handed over to the Customer shall be recalculated, and the amounts payable for works other than the construction works (preparation of the detailed design, technical passports, cadastral files, etc.) shall not be recalculated. In cases where the total Contract Price is revised by agreement of the Parties as a result of the additional works, only that part of the Contract Price for the construction works not handed over to the Customer which was agreed not earlier than twelve (12) months prior to the time of the revision may be recalculated.

3.7.2.7. The decision of the Party receiving the request for recalculation of the price of the Works on the recalculation of the price of the Works (agreement or refusal to recalculate the price of the Works) shall be taken and the other Party shall be notified in writing of the agreement or refusal to recalculate the price within 10 working days from the date on which the other Party's request for recalculation of the price of the Works and all documents supporting the request have been submitted to the other Party according to the terms and conditions of the Contract. If the Party receiving the request for revision of the price of the Works notifies the other Party in writing of its agreement to the revision of the price of the Works, the Parties must conclude an agreement on the revision of the price of the Works within 30 days of the date of the submission to the other Party of the Party's request for revision of the price of the Works and of all supporting documents according to the terms and conditions of the Contract. The Parties must specify In such arrangement the Index values used to calculate the coefficient of the Index, the coefficient of change of the Index, the Contract price to be revised, the recalculated initial value of the Contract and the amount of the Contract performance security, as well as any other information relevant to the revision.

3.7.2.8. A subsequent revision of the Contract price may not include the period already covered by the revision.

3.7.2.9. If, at the time of the revision of the Contract Price, the performance of the Works is delayed for reasons for which the Contractor has not become entitled to an extension of the time for performance of the Works, the part of the Contract Price of the delayed Works may not be revised at the Contractor's initiative due to an increase in the level of prices, but shall be revised if the revision of the Contract Price is initiated by the Client due to a decrease in the price level.

3.7.3. The Contract Price shall be increased or reduced in accordance with the procedure set out in the Contract due to a change in the actual quantity of the Works when the actual quantity of the Works increases or decreases by more than [10] (ten) per cent from the initial value of the Contract, as well as when additional Works are purchased or a part of the Works is abandoned on the grounds set out in Article 97(1)(2) to (5) and (2) of the Law on Procurement by Entities Operating in the Water, Energy, Transport and Postal Services Sectors (hereinafter - the Law).

3.8. The Contract price and the initial value of the Contract shall be changed by bilateral written agreement of the Parties.

3.9. The Contractor shall be paid for the Works performed as follows:

3.9.1. At the Contractor's option, an advance payment may be made to the Contractor within 5 (five) days of the entry into force of the Contract by notifying the Customer in writing of the amount of the advance payment to be made. The amount of the advance to be paid to the Contractor shall not exceed 20% of the Contract Price, excluding VAT, specified in paragraph 3.2 of the Contract, i.e. EUR _______________ (________________________). The advance payment shall be paid to the Contractor within 14 (fourteen) days of the submission to the Customer of the advance payment guarantee referred to in Section 7 of the Contract;

3.9.2. payment for the Work performed, as specified in the Schedule of Quantities and Prices of the Works submitted according to the terms and conditions of subparagraph 8.5.4 of the Contract, shall be made on the basis of the acceptance and handover certificates of the Works performed (Annex 2), and shall be paid to the Contractor within 60 (sixty) days after the date of signing the acceptance and handover certificate of the Works performed and the date of submitting the invoice for payment in accordance with the procedure set out in the Contract. Payments shall be made after deduction of the amount withheld and after offsetting the advance paid to the Contractor if any;

3.9.3. each interim payment shall be offset against the percentage of the advance paid to the Contractor equal to the percentage of the advance paid to the Contractor;

    - in all cases, any part of the advance paid and not offset against previous interim payments shall be offset against the last amounts due. If the last amounts due to the Contractor are smaller than the remaining part of the advance not repaid to the Customer, the Contractor must pay the remaining part of the advance paid to the Contractor within 5 (five) days of the latter’s request;

3.9.5. 5 % (five per cent) of the value of the Works, excluding VAT, shall be withheld for the purpose of rectifying any defects and other deficiencies and for the purpose of covering possible damages, in accordance with the completed Works’ acceptance and handover certificate. The amount withheld shall be paid within 30 (thirty) days from the date of registration of the construction completion document and the expiry of the period for the elimination of any defects and deficiencies, provided that a positive construction assessment report signed by the Contractor, the Customer and the technical supervision representatives has been submitted;

3.9.6. in the event that the total quantity of the Works actually performed is reduced by up to 10% (ten percent) of the initial value of the Contract, 95% (ninety-five percent) of the remaining unpaid portion of the Contract price shall be paid to the Contractor within 30 (thirty) days from the date of signing of the completed Works acceptance and handover certificate of the to the Contractor, on the basis of the invoice submitted in accordance with the procedure set forth in the Contract, 5% (five percent) of the total amount of the Works to the Contractor. The remaining unpaid part of the Contract price shall be paid to the Contractor within 30 (thirty) days from the date of registration of the construction completion document and the expiry of the period for the elimination of any defects and deficiencies, provided that a positive construction assessment report signed by the Contractor, the Customer and the technical supervision representatives is submitted.

3.10. The Customer shall pay to the Contractor the sums of money due under the Contract in euro by means of a payment order to the bank account specified in the Contract. The money shall be deemed to have been paid on the date on which the Client has submitted a payment order to its bank for the payment order.

3.11. In the performance of the Contract, invoices shall be submitted only by electronic means after the Parties have signed the completed Works’ acceptance and handover certificate. Electronic invoices conforming to the European eInvoicing Standard shall be provided by means of the Contractor’s choice. Electronic invoices that do not comply with the European eInvoicing Standard can only be submitted through the General Information System for the management of accounts (SABIS). If the Contractor fails to submit invoices in the manner set out in this paragraph, the Customer shall not make payment and the Customer shall not be liable for late payment as set out in the Contract.

4. CHANGES TO THE QUANTITY (SCOPE) OF WORKS AND OTHER AMENDMENTS TO THE CONTRACT

  - The terms and conditions of the Contract may be amended during the term of the Contract in the cases and on the grounds set out in Article 97 of the Law on Procurement.

  - The Contractor shall bear all risks for the performance of all Works which, although not expressly identified in the Contract, are necessary for the proper execution of the Works under the Contract and for the achievement of the objectives, functionality and results set out in the Contract. Such works shall be a part of the Contract and shall not be considered as additional works.

  - The quantities in the schedule of costs and quantities of the technical design shall be indicative. Changes to the Works and/or materials during the preparation of the detailed design of the Work and the detailing of the solutions of the Technical Design, which result in a change in the quantities indicated in the schedule of costs and quantities of the technical design, shall not be considered as additional and/or non-performing Works and shall not be counted in the percentage specified in subparagraph 3.7.3 of the Contract for changes in the quantities of Works. Additional works shall also not include works provided for in the technical design but not specified in the schedule of costs and quantities, and the replacement of materials without compromising the specifications of those materials provided in the technical design.

  - The Contractor confirms that it has thoroughly analysed the Project presented by the Customer in the procurement documents, and provided for and assessed all of the Works to be carried out under paragraph 1.1 of the Contract, including the delivery or transportation of the Contractor’s personnel and technical resources (materials) to/from the construction site or other location. If the proper performance of the Contract requires the execution of certain works which any professional and reasonable contractor would have anticipated when concluding the Contract but which the Contractor has not provided for and estimated in schedules of costs and quantities, the Contractor shall undertake to execute such Works at its own expense.

  - In the event of abandonment of the Works, substitution of the Works, or acquisition of additional works, the procedure set out in paragraph 4.7 of the Contract shall apply and the Contract price shall be reduced or increased accordingly. Where the actual quantity of the Works increases or decreases within the percentage set out in subparagraph 3.7.3 of the Contract (but not in excess thereof), the Parties shall record such changes in the quantity of the Works in accordance with the procedure set out in paragraph 4.7 of the Contract, without entering into a separate agreement to amend the Contract and without changing the Contract price.

  - A change of Works shall be carried out as the abandonment of the Works to be replaced and the additional purchase of replacement (new) Works. Where the Works are replaced by other works, such replacement of the Works shall not impair the result of the Contract.

  - Abandonment of Works, purchase of additional works, substitution of one Work for another, or other changes in the quantity of the Works shall be effected and recorded in an agreement signed by the Parties, which shall be based on an act of additional (unforeseen) or non-performance of the Works, drawn up and approved in accordance with the prescribed procedure:

    - if it is determined that it is necessary to carry out additional Works, to abandon the Works or to substitute some Works with other Works, the Contractor shall inform the Customer immediately, but not later than within 5 (five) days after the circumstances become apparent, and shall provide the written justification of the need for the abandonment of the Works, additional Works and/or substitution of other Works of the project implementation supervision and technical supervision representatives, as well as confirmation that it is not possible to complete the Works without some or part of the additional works and/or substitution of the Works, or that such additional works and/or substitution of the Works will improve the technical characteristics and features of the Object;

    - The Customer shall, upon receipt from the Contractor of the Contractor’s notification referred to in subparagraph 4.7.1 of the Contract and the approvals of the designer and the head of the technical supervision, invite to the Object the commission consisting of the project implementation supervision, the Contractor, the technical supervision, the Customer’s representatives, and an independent expert (if deemed necessary), within 7 (seven) working days;

    - After the commission has evaluated all the submitted documents and carried out a detailed inspection of the construction site, the Contractor, together with the technical supervision representative, undertakes to draw up and submit to the Customer, within 5 (five) working days from the date of the first meeting of the Commission, an act of additional (unforeseen) or not performed works signed by all the persons who participated in the Commission’s work and detailing the circumstances, the reasons for the occurrence of the additional (unforeseen) or not performed works, assess their validity (necessity) and take a decision on the necessity of the additional (unforeseen) works, the recognition of not performed works, the modification (addition) of the construction documents, the need for the expert’s conclusions, the substitution of certain works with others. Any additional documentation supporting the validity of the additional (unforeseen) or non-performed works (documentation of the construction works, photographs of the existing situation, underwater survey reports or findings, expert reports (if any), etc.) shall be attached to the report;

    - The Customer shall approve the act of additional (unforeseen) or not performed works prepared in accordance with the provisions of the Contract within 7 (seven) working days of its receipt. Upon fulfilment of the conditions set out in the act in respect of the additional works, the Customer shall, within a reasonable time, organise and negotiate with the Contractor the prices of additional works, which shall not be higher than those calculated by applying the methods set out in paragraph 4.9 of the Contract. Following negotiations, the Contractor shall prepare and submit to the Customer a proposal for prices of additional works.

    - On the basis of the act of additional (unforeseen) or not performed works approved by the Customer and, in the case of negotiation of prices of additional works, on the basis of the prices for additional works proposed by the Contractor following the negotiations the Parties shall sign an agreement on amendment to the Contract.

  - The Contractor may commence the execution of additional works once the procedures referred to in paragraph 4.7 of the Contract are finished and a separate agreement for the execution of the additional works is signed. In the event of substitution of certain Works for another in accordance with the procedure set out in the Contract, and in other cases where it is necessary to ensure the continuous performance of the Works, the Contractor may commence the performance of the additional works prior to the signing of the agreement, subject to the approval by the Customer of the proposal of the price of the additional works submitted by the Contractor after negotiations. Permission to commence the additional works prior to the signing of the Contract shall be granted by the Customer by written notice to the Contractor in accordance with the procedure set out in the Contract or by recording such permission during negotiations. If the Contractor violates the procedure set out in paragraph 4.7 of the Contract or carries out additional works without having concluded a separate agreement prior to the commencement of the additional works, except where the Contractor authorises the commencement of the additional works prior to the conclusion of an agreement in the cases set out in this paragraph, the works carried out by the Contractor shall be deemed to be unauthorised and/or carried out in deviation from the normative construction documents. If the Contractor breaches the conditions for the performance of additional (unforeseen) works, it shall be deprived of the right to claim payment of the price of the completed Works from the Customer and the compensation for any losses incurred as a result. The limits of the Contractor’s liability for the result of the completed works when they are performed in an unauthorised manner and/or in deviation from the normative construction documents are defined in paragraph 14.14 of the Contract.

  - In the case of the refusal of the part of the Works, the acquisition of additional (unforeseen) works, or the substitution of certain Works for another works, the following methods for calculating the price of the Works refused or additionally purchased shall apply in the order of priority:

    - applying the rates set out in the Contract;

    - if possible, deducting a part of the price from the rate indicated in the Contract;

    - where possible, by deducting a part of the price from the separate component of the procurement object as priced in the Contract, or from the stipulated rate;

    - assessing the Works’ reasonable direct (wages and related taxes, operating costs of products and equipment, machinery, construction site) and indirect (overheads, profit) costs in accordance with the provisions of the Rules for the Calculation of Direct and Indirect Costs approved by Order No 1S-95 of the Director of the Public Procurement Office of 28 June 2017 on the Methodology for establishing the pricing rules in force and applicable at the time of the change.

  - If additional (unforeseen) or non-performance of the works act necessitates changes to the Project, or the carrying out of an expert examination of the Project, such changes shall be carried out by the Customer.

  - Additional Work shall be paid for in accordance with the payment procedure set out in the Contract.

  - The Customer has the right to refuse up to 30% of the Works which have not been completed by the date of refusal, without paying for them, if the Contractor is late in completing the Works in accordance with the calendar schedule for the execution of the Works, and such refusal of the Works would enable the completion of the object to be accelerated, or for technical and/or technological reasons which may worsen the Customer’s situation (economic, financial), or if it is not appropriate to carry out the Works envisaged in the project documentation, or for any other reason as provided for in the Contract or the procurement documents. The Works shall be abandoned by giving written notice to the Contractor at least 90 (ninety) days prior to the commencement of the Works to be abandoned in accordance with the agreed calendar schedule for the performance of the Works provided by the Contractor. If the Customer refuses the Works in accordance with the terms and conditions of this paragraph, the Contract price shall also be changed if the total quantity of the refused Works does not exceed the percentage of the initial value of the Contract specified in subparagraph 3.7.3 of the Contract. The Contractor confirms that it shall not have any claims or demands, whether pecuniary or non-pecuniary, against the Customer if the Customer refuses certain Works or part of the Works on the grounds set out in this paragraph.

  - The Contract shall be amended by the Parties by signing an agreement on amendment to the terms and conditions, except in the cases provided for in the Contract, where the terms and conditions of the Contract may be amended by unilateral written notice:

    - If the Party’s address, bank account number, contact details, or other particulars of the Party provided for in the Contract change during its validity term, the Parties shall not enter into a written agreement on amendment to the Contract. The Party that changes its particulars or other details must, in accordance with the notification procedure set out in the Contract, inform the other Party in writing of the change;

    - Where the Party has received a request from the other Party to recalculate the price of the Works in accordance with the terms and conditions set out in the Contract and notifies the Party making such request in writing of its agreement to recalculate the price of the Services, the recalculated price of the Works shall apply from the date on which the agreement to recalculate the price of the Works is concluded or from the date on which the other Party was notified of the agreement to revise the price of the Works within the time limit set out in the Contract, whichever is the earlier.

  - Where the Contract is amended for reasons other than changes in quantity (scope), the Customer shall, upon receipt of a reasoned request from the Contractor to amend the terms and conditions of the Contract, decide immediately, but within a maximum of 7 (seven) working days, whether or not an amendment of the terms and conditions of the Contract is necessary. If the Customer decides to amend the terms and conditions of the Contract, the Parties agree to cooperate and collaborate to ensure that such amendment to the Contract, including the completion of all necessary procedures and the signing of the additional agreement(s), is carried out in a timeframe acceptable to both Parties.

  - Amendments to the Contract shall enter into force upon the signature of an additional agreement by both Parties, except in the cases set out in the Contract where additional (unforeseen) works may commence prior to the signing of the additional agreement.

5. SUSPENSION OF PERFORMANCE OF THE CONTRACT

  - In the event of reasonably significant circumstances, the Contractor shall have the right to suspend the execution of the Works or any part thereof in the following manner:

    - Upon receipt by the Customer of the Contractor’s written notification containing the relevant circumstances, the Customer shall objectively assess the circumstances received and accept or reject the relevant circumstances in writing;

    - At the initiative of the Customer, when the Customer is unable to hand over the construction site to the Contractor within the preliminary deadline set out in the Contract due to not completed construction works in the Object by another contractor, and (or) when the latter establishes important objective circumstances for the suspension of the Works or of any part of the Works.

  - If the performance of the Works is suspended for more than 60 (sixty) days at a time (by a single notice) and the suspension is not due to the fault of the Contractor (except where the Customer is unable to hand over the construction site to the Contractor within the time limit set out in the Contract due to the incompletion of the construction works in the Object by another contractor), the Contractor may, at the end of the period of 90 (sixty) days, request the Customer in writing to resume the performance of the Works within thirty (30) days after the receipt by the Customer of such request. If the Customer fails to resume performance of the Works at the request of the Contractor, the Contractor shall be entitled to initiate termination of the Contract by agreement between the Parties.

  - The performance of the Contract may be suspended when the Customer is unable to hand over the construction site to the Contractor within the time limit set out in the Contract due to the execution of construction works in the Object by another contractor, or in order to verify whether material errors or irregularities have actually occurred, as well as in the following cases, where inaccuracies in the technical documentation are identified and/or reasonable solutions are provided by the parties to the Contract to improve the intended result of the Contract and/or reasonable assumptions are made for the occurrence of works that are not appropriate/possible to be included in the performance of the Contract. If the suspicions or other assumptions referred to above are not confirmed, the Contract shall be reinstated. A material error or breach means any breach of the Contract, applicable law or court decision resulting from an act or omission. In this case, the Customer shall not be subject to any penalties or claims for any damages (e.g. loss of revenue, profit, absenteeism, etc.) provided for in the Contract or by the legislation for the suspension of the Contract, and the Contractor shall not be subject to any penalties or claims for failure to meet the deadlines for performance of the Works, provided that it is established that the said material error or irregularity is not due to the Contractor.

  - When, due to important, objective circumstances arising during the performance of the Contract, or in order to ascertain whether material errors or irregularities have actually occurred, or when the Customer is unable to hand over the construction site to the Contractor within the time limit set out in the Contract due to construction activities being carried out by another contractor in the Object, the performance of the Contract is suspended and the time limits for the completion of the Works are suspended. Upon resumption of performance of the Contract, the time for performance of the Works shall be extended to the extent of the time remaining to the Contractor before the suspension of the Contract. If the material error or irregularity is found not to be the fault of the Contractor, the Contractor shall not be entitled to make any claim against the Customer, including any claim for damages, or to impose any sanction on the Customer.

6. INSURANCE

6.1. Within 10 (ten) days after the Contract comes into force, the Contractor, having agreed with the Customer on the insurance conditions, shall be obliged to take out, at its own expense, compulsory insurance for the construction, reconstruction, repair, renovation (modernization), demolition or r management construction works of a cultural heritage building and civil liability insurance in accordance with the requirements of Chapter XI ("Compulsory Insurance") of the Law of the Republic of Lithuania on Construction and to submit to the Customer the certified copies of the insurance certificate issued by the insurance company to the Contractor for the construction of the building, reconstruction, repair, renovation (modernisation), demolition or management construction works of a cultural heritage building and the compulsory insurance certificate (policy) and of the payment order confirming that all or the first part of the insurance premium has been paid. If the insurance premium is payable in instalments, the Contractor must, within 10 (ten) days after the payment of each premium specified in the insurance certificate (policy), submit to the Customer a certified copy of the document evidencing its payment.

6.2. Compulsory insurance shall cover the Contractor's construction Works and civil liability in respect of each new building being constructed, reconstructed or demolished (where the insurance object is as defined in Article 42(3) of the Construction Law) for the entire period of performance of the Works on a property unit basis:

6.2.1.Northern Dam (Part I), the sum insured shall not be less than EUR 250 000 (two hundred and fifty thousand euro) per insured event for the entire period of performance of the Works;

6.2.2.South Dam, the sum insured shall not be less than EUR 250 000 (two hundred and fifty thousand euro) per insured event for the entire period of performance of the Works;

6.2.3. for each other newly constructed, reconstructed or demolished building not less than EUR 43 400 (forty-three thousand four hundred euro) per insured event for the entire period of performance of the Works.

6.3. If the time limit for performance of the Works is extended, or if, in the absence of such extension, the Contractor has not completed the performance of all its obligations by the expiry of the compulsory insurance policy, the Contractor shall be obliged to extend (renew) the compulsory insurance contract at its own expense and to submit to the Customer the documents referred to in paragraph 6.1 for the full period of performance of the Works.

  - If the Contractor fails to submit the documents referred to in this Section in time, the Customer shall have the right to withhold payment for the Works until the insurance policies have been submitted or to terminate the Contract.

7. GUARANTEE OF PERFORMANCE OF THE CONTRACT AND REPAYMENT OF THE

ADVANCE PAYMENT

  - Where paragraph 2.1 of the Contract stipulates that its entry into force is conditional upon the provision of a performance security, the Contractor shall, within 10 (ten) days after the signature of the Contract, provide the Customer with an irrevocable first demand performance security for the Contract, in the form of a bank guarantee or a surety bond from an insurance company, in the amount of ten 10 (ten) percent of the initial value of the Contract, and shall provide documents confirming that the Contractor has paid all the required instalments for the Contract performance security document. Where the Initial Value of the Contract has been recalculated in accordance with the procedure set out in the Contract, its performance security document for the recalculated amount of the security shall be lodged no later than within 10 (ten) days after the date of conclusion of the agreement to recalculate the Contract price.

  - A draft Contract performance security document shall be submitted to the Customer for coordination. The term of validity of the Contract performance security document must be at least 30 (thirty) days longer than the total period of performance of the Works. The Contract performance security document must be valid for all of the Contractor’s obligations under the Contract, including fines, penalties, interest and other costs reasonably claimed by the Customer. The Contract performance security document shall provide that the security amount shall be payable to the Customer not later than within 15 days after the first written notice from the Customer to the issuing entity stating the amount claimed and specifying the non-compliance with contractual obligations.

  - In the event that the time limit for the performance of the Works is extended, or if the Contractor has not completed the performance of all its obligations under the Contract without such extension, the Contractor must, not later than ten (10) working days prior to the expiry of the period of validity of the Contract performance security document, provide an extended Contract performance security document for the duration of the extension of the time limit for the completion of the Works and where the Contractor has not completed all of its obligations without an extension of the time limit for the completion of the Works, for a period of time sufficient to ensure that the Contract performance security document remains valid for at least 30 (thirty) days after the Contractor has fully performed its obligations.

  - If the Contractor fails to extend the validity of the Contract performance security document, or fails to provide a Contract performance security document for the recalculated initial value of the Contract in the cases set out in the Contract, the Customer shall have the right to suspend payments under the Contract and/or terminate it.

  - Where the Contractor chooses to receive an advance payment in the amount specified in the Contract, the Contractor must, within 60 (sixty) days of the entry into force of the Contract, provide an irrevocable, first demand, unconditional advance repayment guarantee in the amount of the advance payment to secure the repayment. The advance repayment guarantee shall be submitted to the Customer for coordination.

  - The advance repayment guarantee must be issued by a reputable bank which (or a parent bank of which) has a credit rating not lower than Standard & Poor's - BBB+, or Moody's - Baa1, or Fitch - BBB+) (the guarantee must be valid for the period referred to in paragraph 7.2 of the Contract or until the repayment of the advance, but may be progressively reduced by the amounts of the advance amounts repaid by the Contractor as specified in the completed Works’ acceptance and handover certificates.

  - If the Contractor is late in completing the Works within the time limit for completion of the Works, not less than ten (10) working days prior to the expiry of the advance payment guarantee, the Contractor must provide an extended the advance payment guarantee for the outstanding amount of the advance, which shall be for a period of at least thirty (30) days after the full implementation of the Contract. If the Contractor not extend the validity term of the advance payment guarantee, the Customer shall have the right to suspend payments under the Contract for that part of the advance payment which has not been offset.

8. RIGHTS AND OBLIGATIONS OF THE PARTIES

8.1. The Customer undertakes:

8.1.1. to hand over the Project, the CP and the Construction site to the Contractor by the Acceptance and Transfer Certificate within the time limits set in the Contract;

8.1.2. where the Works or part of the Works are carried out using the Customer's materials, to hand over to the Contractor by means of an acceptance- handover certificate the Customer's materials specified in the Contract prior to the commencement of the Works, in accordance with the calendar schedule for the performance of the Works;

8.1.3. to notify the Contractor of who will carry out the construction technical supervision of the Works, and control and supervise the scope, duration and quality of the Works;

8.1.4. to notify the Contractor immediately in writing in the event of any defects or deficiencies or deviations from the Conditions which impair the quality of the Works;

8.1.5.to accept the Work from the Contractor under the Contract, to inspect the Works and to notify the Contractor in the event of any deviations from the terms of the Contract or other defects;

8.1.6. to accept from the Contractor the duly completed Works and pay for them in accordance with the conditions set out in the Contract.

8.2. The Customer shall supervise the performance of the Works under the Contract and shall give the necessary instructions for the performance of the Works under the Contract, and shall have the other rights and obligations of the Customer as provided for in the Contract and legal acts.

8.3. General obligations of the Contractor:

8.3.1. to maintain, throughout the term of the Contract, the qualifications at least equivalent to the qualification requirements set out in the procurement documents and the compliance with the mandatory requirements set out in the procurement documents. If the Contractor’s qualifications for the activity in question have not been verified at all or in full during the procurement procedure, it is necessary to ensure that the Contract is performed only by persons who are qualified to carry out the activity. If the Contractor intends to replace the professional(s) whose qualifications it has relied on to justify its compliance with the qualification requirements, it must inform the Customer in writing and provide the documents confirming the qualifications of the replacement professional. The Customer shall, upon receipt of a request from the Contractor for a change of a professional, verify, not later than within 7 (seven) days, whether the qualifications of the new professional meet the requirements of the procurement documents and shall notify the Contractor in writing of its agreement to the change of the professional, or shall provide a reasoned refusal;

8.3.2. to ensure that the construction managers appointed by the Contractor and/or by subcontractors appointed by the Contractor, who for the purpose of performance of the Contract will require the right of unescorted access to the facilities or assets of national security importance managed by Klaipėda State Seaport Authority, will meet the criteria set out in Article 17(2) of the Law of the Republic of Lithuania on the Protection of Objects of Importance to National Security and to submit the documents specified in the Law to the Customer for verification prior to the appointment or replacement of any construction manager(s) who have been appointed;

8.3.3. to protect and not disclose to third parties classified information and confidential information obtained in the performance of the Contract, and, at the request of the Customer, sign an agreement on the protection of classified information or confidential information;

8.3.4. to comply with the procedure for notification of additional or refused works set out in the Contract;

8.3.5. to comply with the procedure set out in the Contract for notification of contact details of subcontractors and of the use of representatives, replacement, additional and new subcontractors;

8.3.6. to inform the Customer in writing within 5 (five) calendar days of any significant circumstances (such as seizure of assets or application of interim measures of protection, conclusion of an amicable agreement with creditors, the occurrence of grounds for bankruptcy or restructuring proceedings, the filing of petitions for the opening of bankruptcy or restructuring proceedings against the Contractor, the initiation of a bankruptcy or restructuring case, or a tax debt, etc.) that affect or may affect the fulfilment of the contractual obligations;

8.3.7. to comply with the requirements of occupational safety, fire safety, hygiene, environmental protection, the requirements of the Regulations for Klaipėda State Seaport Operations and Navigation and to be responsible for their implementation and the consequences of any violation of their requirements;

8.3.8. to enable and not prevent and not interfere with another contractor carrying out additional works within the boundaries of the construction site, if there are any such works in the Object carried out by another contractor and, in accordance with the procedure set out in the Law, the performance of such works has been assigned to another contractor;

8.3.9. to ensure that employees of the Contractor or of subcontractors of the Contractor and/or third parties carrying out the Works are not under the influence of alcohol, narcotic, toxic and/or psychotropic substances during the performance of the Works on the construction site;

8.3.10. to get acquainted with and to observe the description of the anti-corruption policy of Klaipėda State Seaport Authority (hereinafter - the Policy) and the Code of Conduct for Business Partners of  Klaipėda State Seaport Authority (hereinafter - the Code) in dealings between the Customer and third parties. The Policy and the Code, and any amendments thereto are posted at http://www.portofklaipeda.lt. The Contractor must ensure that the requirements of this paragraph and the Policy and the Code are complied with by the Contractor’s employees and other representatives of the Contractor and of any third parties it engages to perform the Contract;

8.3.11. to comply with environmental, social and labour law obligations set out in the legislation of the European Union and the Republic of Lithuania, in collective agreements and in the international conventions referred to in Annex 7 of the Law;

8.3.12. at the request of the Contractor, to provide documents justifying compliance with the environmental criteria for the products specified in the description of the procedure for the application of environmental criteria in green procurement approved by the Order of the Minister of the Environment of the Republic of Lithuania of 28 June 2011 No. D1-508 "Concerning the Approval of the Description of the Procedure for the Application of the Environmental Criteria in the Conduct of the Green Procurement" of the Annex 2 to Sections XIII - XVI thereof, which are subject to minimum environmental criteria;

8.3.13. at the request of the Contractor, to provide documents confirming the registration of the Contractor, the subcontractor, the economic entity on whose capacities the Contractor relies, documents certifying the registration of the manufacturer of the goods (including their component parts) to be used in the execution of the Works, or of the legal entities controlling such entities, or of the residence and nationality of the natural persons, as referred to in the Law, as well as documents confirming the origin of the goods supplied or used in the performance of the Works, as provided by the manufacturer or another third party;

8.3.14. to provide the documents specified in the Contract or requested by the Customer in the form and format specified in the Contract and, where not provided for in the Contract - in the form and format specified by the Customer’s manager;

8.3.15. at the request of the Customer and by granting access granted to the Contractor’s authorised person, at the intervals specified in the Contract or by the Customer's Project Manager, to record information corresponding to the actual progress of the Works, the information relevant to the performance of the Contract, and other information requested by the Customer's Project Manager to be included in “Let's build” software;

8.3.16. to ensure that all persons performing the Works in the construction site have a transparent worker’s identification code established in accordance with the procedure set by legal acts, and other persons at the construction site have an identification tool specified by the Contractor for other persons at the construction site; establish the procedure for issuing identification tools for other persons at the construction site; register the time and reason for the beginning and end of the stay of other persons at the construction site and perform other duties established by the legal acts of the Republic of Lithuania relating to the identification of the persons present at the construction site. Where joint activity partners act on behalf of the Contractor, the duties set out in this paragraph shall be performed by the responsible joint activity partner;

8.3.17. The Contractor shall be obliged to continuously monitor and identify the risks related to sanctions compliance within the scope of the Contractor's activities, to be familiar with and comply with the provisions of the Employer's Sanctions Enforcement and Control Policy (https://portofklaipeda.lt/wp-content/uploads/2024/10/Sankciju-politika.pdf), or to have itsown internal documentation for the implementation of the sanctions compliance requirements, which is in line with the Customer‘s Sanctions Enforcement and Control Policy, and to ensure that these requirements are complied with by the economic operators on whose capacities the Contractor relies, and by the Contractor's subcontractors;

8.3.18. The Contractor undertakes not to publish (make public) in any form press releases, promotional information, social media posts or other information relating to the Customer, the performance of this Contract or the Contract Project without the prior written consent of the Customer. The Client shall decide on the consent referred to in this clause within 5 (five) working days on the basis of a written request from the Contractor, submitted to the Customer together with the final content to be published (text, visual material, etc.). Failure to provide consent within 5 (five) working days after the submission of all the information referred to in this clause to the Customer shall be deemed to be the Customer‘s refusal to consent to the publication of the relevant information. The Contractor shall be liable to pay a fine of EUR 1 500 (one thousand five hundred euro) for each instance of non compliance for each instance of publication of information in breach of the requirements set out in this clause, at the request of the Customer.

8.3.19. to duly perform the other duties assigned to the Contractor under the Contract and the applicable legal acts.

8.4. The Contractor confirms that at the time of conclusion of the Contract, the Contractor, its subcontractors and the entities whose capabilities the Contractor relies on are not subject to any international sanctions and/or international sanctions of other countries (the United Kingdom or the United States of America), and/or other restrictive measures imposed by laws of the Republic of Lithuania, which are or may be applicable in the Republic of Lithuania and which may have an effect on the performance of the Contract. Should the sanctions or restrictive measures referred to in this paragraph be imposed on the Contractor or on entities whose capabilities have been relied upon by the Contractor in the performance of the Contract, the Contractor undertakes to notify the Customer in writing without delay and, should sanctions or restrictive measures be imposed on the Contractor’s subcontractors, to remove such subcontractors from the performance of the Contract and, if necessary, to replace such subcontractors in the manner provided for in the Contract. The Contractor who is in breach of its obligations under this paragraph of the Contract, and in the event that the Contractor’s representations set out in this paragraph are found to be untrue, must indemnify the Customer against any loss arising from such breach and inconsistency, including, but not limited to, loss arising from termination of the Contract.

8.5. Special Obligations of the Contractor:

8.5.1. to plan and execute the Works in accordance with the requirements set out in the normative construction documents, the procurement documents and the provisions of the Contract in order to ensure that they are carried out in a high-quality and timely manner;

8.5.2.to accept the technical design, the CP and the construction site within the time limits set out in the Contract by means of an acceptance and Transfer Certificate;

8.5.3. to submit an agreed calendar schedule for the completion of the Works according to the time limits and procedure set out in the Contract;

8.5.4.after the preparation of the detailed design or part of the design, after its initial examination by the Customer, to submit, at the Customer‘s expense, within 10 (ten) days after the receipt of the positive examination report, a completed (detailed) price and quantity schedule of the Work at the Customer‘s expense in accordance with a separate agreement concluded between the expert and the Customer, indicating the price of each work and material separately. In the absence of a positive conclusion of the expert examination of the detailed design, the Contractor shall immediately revise the detailed design to be prepared in accordance with the comments of the expert. Re-examination(s) in the event of failure to obtain a positive expert opinion due to the fault of the Contractor shall be carried out by the Customer and the costs incurred by the Customer shall be reimbursed by the Contractor. The Customer may in all cases require justification of the prices of individual parts of the detailed design or individual Works/materials;

8.5.5.commence the Works on the Object only after receipt of the Design with the Technical Supervisor's stamp of " I approve the construction " and having obtained the prepared and aligned Design Technology of Works;

8.5.6. take over the materials handed over by the Customer signing the acceptance and handover certificate and to store them in compliance with the requirements of the construction technical regulations and rules and technical specifications, enable the technical supervisor and the Customer to inspect the materials handed over to the Contractor by the Customer stored outside the construction site, when the Works are carried out using the Customer's materials;

8.5.7. ensure the protection of the material assets in the Object and be responsible for any damage, destruction or loss thereof;

8.5.8. inform the Customer of the need to modify or revise the approved technical design or detailed design;

8.5.9. formalize the documentation of the execution of the Works, to fill in the Work logs, and to submit the originals of all these documents within 5 (five) days upon the Customer's request during the execution of the Contract. If the Contractor loses the documents related to the performance of the Works, the Contractor must restore them at own expense;

8.5.10. submit interim Works’ acceptance and handover certificates in accordance with the procedure and deadlines set out in the Contract

8.5.11. prepare and submit to the Customer properly prepared mandatory construction completion documents within the time limits set out in the Contract and to participate in the construction completion procedures. prepare and/or update the technical passports of the buildings of the Object upon completion of the Works;

8.5.12. within 10 (ten) days of the defects becoming apparent, start rectifying, at own expense, any defects that have arisen during the performance of the Works and during the warranty period;

8.5.13. to manage construction waste in accordance with the Construction Waste Management Regulations, in accordance with the instructions of the Customer, where such instructions are provided;

8.5.14. on every working day by 10.00, submit to the Customer’s project manager an electronic report on the Works in Microsoft Project format and/or any other format requested by the Customer, indicating the Work carried out at the Object until the date of the report and the works planned to be completed during the coming week. The Contractor shall provide such data promptly at the request of the Customer;

8.5.15. provide, at the request of the Customer, a local estimate of the Works and other documents related to the performance of the Contract;

8.5.16. together with the report for each current month submit the schedule of Works actually completed in Microsoft Project format and/or in any other format requested by the Customer by the 7th (seventh) day of the following month in the form approved by the Customer and in the event of delay from the agreed calendar schedule for the completion of the Works, give reasons for the delay, and provide for and specify the measures and time limits for the elimination of the delay in the Works without any additional costs to the Customer The schedule of Works actually completed for the current month shall be signed and dated by the Contractor's designated representative;

8.5.17. after the completion of the Object has been documented by the Construction Completion Document and registered in IS "Infostatyba", submit to the Customer, within 30 (thirty) days at the latest, a positive Construction Assessment Certificate signed by the Contractor, the Customer and the technical supervision representatives.

8.5.18. Implement the measures on birds set out in the screening report on the environmental impact assessment. Provide documentation supporting compliance with the measures upon request of the Employer.

8.5.19. In the event of motivated noise complaints from persons living in the vicinity of the contractor's works, the contractor shall carry out noise measurements in accordance with the provisions of the Lithuanian Hygienic Standard HN 33:2011 "Noise Limits in Residential and Public Buildings and their Surroundings" approved by the Order No. V-604 "On Approval of the Lithuanian Hygienic Standard HN 33:2011 "Noise Limits in Residential and Public Buildings and their Surroundings" (hereinafter referred to as the "Lithuanian Hygienic Standard HN 33:2011") and, in accordance with the results obtained, shall control the operating mode of the machinery in such a way as to ensure that there is no violation of the Lithuanian Hygienic Standard HN 33:2011.

8.5.20. During the execution of the works, the project shall be guided by the requirements of the Rules of Noise Prevention in Public Places of Klaipėda City Municipality, approved by the Klaipėda City Municipal Council Decision No T2-321 of 21-12-2017 "On the Approval of the Rules of Noise Prevention in Public Places of the Klaipėda City Municipality", as well as by the Action Plan of the Klaipėda City Municipality for the Prevention of Noise in Public Places of the Klaipėda City Municipality, approved by the Decision of the Klaipėda City Municipal Council No T2-241 of 25-07-2019 "On the Approval of the Klaipėda City Municipal Noise Prevention Action Plan for the Years 2019-2023".

8.6. All results and related rights acquired in the performance of the Contract, including copyright and other intellectual or industrial property rights, shall belong to the Customer.

8.7. Neither Party shall be entitled to assign all or part of its rights and obligations under this Contract to any third party without the prior written consent of the other Party.

9. PERFORMANCE OF WORKS

9.1. The Works shall be carried out in accordance with the calendar schedule for the completion of the Works. The Contractor shall submit the final agreed calendar schedule for the completion of the Works to the Customer not later than within 30 (thirty) days after the date of entry into force of the Contract in accordance with the prescribed procedure:

9.1.1. not later than within 14 (fourteen) days after the date of entry into force of the Contract, the Contractor shall agree in writing on the calendar schedule for the completion of the Works with the technical supervision manager and the port operator in whose leased port area the Works will be carried out;

9.1.2. if the technical supervision manager and the port operator in whose leased port area the Works will be carried out refuse to agree on the calendar schedule for the completion of the Works, the Contractor shall take into account the comments made and revise the schedule to incorporate the proposals made, or shall reasonably refuse to do so. The Contractor shall submit the revised calendar he calendar schedule for the completion of the Works and the related correspondence documentation to the Customer not later than within 5 (five) days after the expiry of the deadline set out in subparagraph 9.1.1 of the Contract;

9.1.3. the Customer must sign the submitted calendar schedule for the completion of the Works or provide reasoned comments within 5 (five) days of receipt of the calendar schedule for approval;

9.1.4. if any comments have been provided regarding the calendar schedule for the completion of the Works, the Contractor shall, within the remaining 5 (five) days, assess the comments made by the Customer and submit the final agreed schedule to the Customer;

9.1.5. The Contractor must additionally provide the Customer with the agreed calendar schedule for the completion of the Works in electronic form in Microsoft Project format and/or in any other format requested by the Customer.

9.1.6. The calendar schedule for the completion of the Works shall be amended by bilateral agreement for the extension of the time limit for the for the completion of the Works, in accordance with the procedure for the extension of the time limit for the for the completion of the Works set out in the Contract, and for the suspension of performance of the Contract.

9.2. The calendar schedule for the completion of the Works, agreed in accordance with the terms and conditions of the Contract shall constitute an integral part of the Contract.

9.3. The Customer shall hand over to the Contractor the construction site of the specified size according to the Design and Zones of Works in the manner prescribed by the Contract:

9.3.1. the Contractor must, within 10 (ten) days of being provided with the Design, submit to the Customer for approval a plan of the construction site’s coordinated with the technical supervision manager, the port operator and, if necessary, other interested parties;

9.3.2. the Customer, upon receipt of the agreed construction site plan from the Contractor, shall, within 5 (five) days, approve the construction site plan and provide the Contractor with the construction site acceptance and handover certificate, or shall refuse to approve the construction site plan informing the Contractor in writing of the reasons for such refusal. If the Customer refuses to approve the construction site plan the Contractor shall immediately adjust it in accordance with the Customer's comments and resubmit it to the Customer for approval;

9.3.3. the Contractor shall take over the construction site within 5 (five) days after receiving the site acceptance certificate from the Customer;

9.3.4. if the Contractor fails to accept the construction site within the set time limit, the Customer shall be deemed to have handed over the construction site to the Contractor on the 6 (sixth) day after the date of dispatch of the construction site acceptance and handover certificate to the Contractor.

9.4. In carrying out the Works, the Contractor:

9.4.1. before the commencement of the Works, on agreement with the person carrying out technical supervision, the person carrying out the project implementation supervision and the port operator’s representative, shall submit to the Customer the Works technology design in PDF format and the original paper version. The Works technology design shall include temporary measures to protect the construction site, equipment and people from external factors during performance of the Works, so that the Contractor's performance of all Works of the Object according to the Design does not endanger the stability of the shoreline and the structures located in the area leased by the port operator;

9.4.2. shall obtain permits or coordinate the performance of the Works in the buffer zones (power grids, communication lines, trunk pipelines, etc.), on the carriageway of urban streets, on the railway and road sections in operation for the purpose of tree felling, excavation works, etc. The Customer shall provide a permit for the tree felling or other removal of vegetation (in accordance with the vegetation survey) in the construction area and in the area for the erection of temporary structures, but the Contractor shall obtain a supplementary permit if required;

9.4.3. on agreement with the Customer and the organisation operating the engineering networks, shall arrange for the disconnection of existing engineering networks and the connection of newly constructed engineering networks and communications to existing networks;

9.4.4. must immediately submit its doubts in writing to the Customer:

9.4.4.1. regarding the quality of the materials provided by the Customer or the quality of the works carried out by other contractors (if any);

9.4.4.2. regarding various other circumstances beyond the control of the Contractor which threaten the adequacy, soundness, safety of the Works;

9.4.5. must compensate, on own account, for the Works which, at the time of performance, are deemed to be defective or non-compliant with the Contract, and to make good any resulting losses. If the Contractor fails to comply with its obligations and to remedy the deficiencies, the Customer may set the respective time limit for remedying such deficiencies;

9.4.6. shall carry out all processes of the Works in such a way that existing structures are not used without the need or improperly;

9.4.7. shall clear the construction site after the completion of the Works under the Contract. If the Contractor fails to clear the construction site by the deadline set by the Customer, the Customer shall be entitled to clear the construction site at the Contractor's expense by using third parties;

9.4.8. shall repair the storage, worksite, access roads and other facilities provided by the Customer to their previous condition;

9.4.9. if the Works or any part thereof are carried out using materials supplied by the Customer and unless otherwise specified by the Customer, the materials, construction products and articles supplied by the Customer shall be unloaded, transported and stored by the Contractor at its own expense;

9.4.10. shall not use subcontractors for the execution of the Works and shall not rely on capacities of economic entities during mobilisation, war, state of emergency or where the Government of the Republic of Lithuania has assessed the risk that factors which have led or may lead to the declaration of mobilisation, the imposition of martial law or a state of emergency threaten national security, and shall not supply and shall not use for the Works any goods (including their components, packaging) whose manufacturer’s place of registration or the place of registration of the legal entity controlling any of the above-mentioned entities, or the place of permanent residence of the natural person, or the state of citizenship of the natural person, is included in the List of Hostile Countries and Territories approved by the Government of the Republic of Lithuania (hereinafter - the List), shall not supply and shall not use for the Works any goods (including their components, packaging) whose country or territory of origin is included in the List, and shall not provide services which are provided from the countries or territories included in the List. Where compliance with the requirements of this paragraph has been verified during the procurement process leading to the Contract, the Contractor must promptly inform the Customer of any changes to this information or of any new information that emerges during the performance of the Contract.

10. ACCEPTANCE OF COMPLETED WORKS

10.1. Once a month, upon completion of the Works under the Contract, the Contractor and the Customer shall mutually sign a handover and acceptance certificate confirming that the Works have been satisfactorily completed during the reporting period. The certificate of acceptance and handover of completed Works shall be drawn up and signed in accordance with the established procedure:

10.1.1. Contractor shall submit to the technical supervision representative and to the Customer's authorised person a certificate of acceptance and handover of completed Works in the form specified in the Contract in electronic format (Microsoft Project and/or any other format requested by the Customer) and in paper format signed by the Contractor's authorised person (3 copies). The certificate of acceptance and handover of completed Works should specify all the Works carried out during the calendar month for which the certificates of completion of the Works are submitted, and the price of those Works. The certificates of completion of the Works should be drawn up in a way that allows verifying each amount indicated in them.

10.1.2. At the request of the Customer, the Contractor shall provide, together with the certificate of completion of the Works the estimate confirming the type and extent of the Work and documents confirming the quality of the materials used for the Work (in the case where the Work has been carried out with the Contractor's materials);

10.1.3. the technical supervision representative shall inspect and evaluate the quality and quantity of the Works carried out during the reporting period and shall confirm by signature his approval of the submission of the certificate of acceptance and handover of completed Works to the Customer;

10.1.4. within 5 (five) days after the approval by the technical supervision representative, but not later than by the 5 (fifth) day of the following month, the Contractor shall submit to the Customer the 3 copies of the acceptance and handover certificate of the completed Works signed by the Contractor's authorised persons and the technical supervision representative;

10.1.5. the Customer shall, within 5 (five) working days, examine and, if there are no comments, sign the acceptance and handover certificates of the completed Works or, if there are comments (if errors, discrepancies, inaccuracies or additions, adjustments, clarifications, etc., are found in the certificates, or if supplements, amendments, explanations, etc., are required), return them with the written comments to the Contractor for correction;

10.1.6. after the Customer has signed the acceptance and handover certificate of the Works completed by the Contractor, the Contractor shall submit an invoice to the Customer within 2 (two) days in accordance with the procedure set out in the Contract.

10.2. Upon signing the certificate of acceptance and handover of completed Works, the risk of accidental loss or damage to the Object, as well as the obligation to take care of the Object or any part of it, shall rest upon the Contractor until the signing of the certificate of handover of completed Works by the Contractor to the Builder.

10.3. Upon completion of all the Works, Contractor must apply to the Customer in writing for the handover and acceptance of the completed Works.

10.4. Upon receipt of the Contractor's notification of readiness to hand over the completed Works, the Customer must, within 5 (five) days:

10.4.1. carry out a general examination and inspection of the Works together with the head of the technical supervision of the building construction. The head of the technical supervision of the building construction must draw up the certificate of acceptance and handover of completed Works stating in it that the Works were completed in accordance with the Contract, also attaching (if applicable) a list of defects and small works that have not been completed which will not materially affect the use of the Works for their intended purpose. Such list shall specify by when the unfinished Works are to be completed or defects remedied. The handing over and acceptance of the Works shall be evidenced by a certificate of handover of the completed Works to the Builder signed by both Parties.

10.4.2. refuse in writing to accept the Works, stating the grounds for the refusal and specifying the Works that the Contractor must carry out in order to be able to sign the Works handover and acceptance Certificate and to initiate the construction completion procedure.

10.5. Before acceptance of the Works, tests and control measurements should be carried out and the results obtained shall be at least as good as those specified in the Design.

10.6. Together with the acceptance and handover certificate of the completed Works the Contractor must submit to the Customer the mandatory construction completion documents, already verified and approved by the technical supervision head as suitable and fully completed, prepared in accordance with requirements of STR 1.05.01:2017 "Construction permit. Completion of construction. Suspension of construction. Removing the effects of arbitrary construction. Elimination of consequences of Construction that permit issued illegally”. Completion of construction. Suspension of construction. Removing the consequences of unauthorised construction. Removing the consequences of construction carried out according to an unlawfully issued construction permit" requirements.

10.7. The Contractor shall be liable to the Customer for deviations from the requirements of the normative construction documents and, if defects in the Works are found, the Contractor shall remedy them at its own expense.

10.8. Completion of the Object shall be documented by a construction completion document, when the document is signed by all members of the commission without any comments and registered in IS Infostatyba.

11.TERMINATION OF THE CONTRACT

  - The Contract may be terminated on agreement of the Parties or at the initiative of one of the Parties on the grounds set out in the Contract.

  - The Customer shall have the right to unilaterally terminate the Contract out of court by giving 15 calendar days’ written notice to the Contractor in accordance with Article 6.217(1) and (3) of the Civil Code and the following grounds:

    - if the Contractor, despite the Customer’s urging, fails to start the Works at the agreed time or works so slowly that the deadlines set out in the calendar schedule for the performance of the Works are breached and it would be reasonably impossible to complete the Works within the time limit set out in the Contract;

    - If the Contractor fails to comply with the terms of the Contract. regarding the quality of the Works by using inappropriate materials or other components, performing the Works or part of the Works in a substandard manner, disobeying the Customer’s instructions to remedy deficiencies within the specified time limits, or behaving in a manner different from that set out in the Contract., and the Customer, therefore, has reason to believe that the Contractor is incapable of completing the Works without material defects or significant loss to the Customer;

    - if there are material deviations from the terms and conditions of the Contract in the Works carried out by the Contractor or other material deficiencies in the performance of the Contract;

    - if it transpires that, in the pursuit of the Contract, the Contractor has entered into an agreement that impermissibly restricts competition;

    - if it becomes known that the Contractor is subject to seizure of assets or interim measures, the Contractor has concluded a composition agreement with creditors, grounds for opening bankruptcy or restructuring proceedings have arisen, a petition has been filed for opening of bankruptcy or restructuring proceedings against the Contractor, or bankruptcy or restructuring proceedings have been initiated, or there are tax arrears, the extended Contract performance security is not provided, the civil liability insurance is not renewed or other relevant circumstances exist, and the totality of the information gathered suggests that the Contractor will not be able to implement the Contract time, or that the Works may be performed in a substandard manner, or that the recovery of damages resulting from a breach of the Contract may be impeded;

    - if, as a result of a reorganisation of the Contractor, including a merger and demerger, separation or bankruptcy proceedings, the successor to the Contractor is unable to continue to perform the Contract on the same terms and conditions in an adequate manner, and does not provide, at the request of the Customer, reliable evidence of the feasibility of the performance of such obligations in the future;

    - if, due to Force Majeure, the Works have to be postponed for an indefinite period of time, or if the Force Majeure event lasts longer than 3 (three) months;

    - if the Contractor, in violation of the requirements of the legislation of the Republic of Lithuania, discloses to third parties classified information which has become known to the Contractor in the course of performance of the Contract;

    - if the Contractor fails to comply with its obligations under the Contract in relation to the submission and renewal of the compulsory insurance, the implementation of the Contract, the provision of advance repayment security documents set out in the Contract;

    - if the Contractor (or any of the Contractor’s employees, agents, subcontractors, representatives, etc.) gives or offers (directly or indirectly) to any employee of the Customer any bribe, gift, gratuity, commissions, services or other item of value as an inducement or reward for doing or refraining from doing any act in connection with the Contract, or for showing, or refraining from showing, any favour or disfavour to any person connected with the Contract. The Contractor must indemnify the Customer against all losses incurred as a result of the termination of the Contract;

    - the grounds set out in Article 98(1) of the Law and those established in other legal acts.

  - The Contractor shall have the right to terminate the Contract by giving 15 calendar days’ written notice to the Customer if the Customer has unreasonably ceased to make mandatory payments and is in arrears or is in default of other material obligations under the Contract and, notwithstanding the Contractor’s requests in writing, has failed to take steps to remedy the situation, except where the Contract is suspended in the manner provided for in the Contract.

  - If any of the Contractor’s confirmations provided for in paragraph 8.4 of the Contract appear to have been erroneous or if any of the obligations are not fulfilled, or if during the performance of the Contract it becomes apparent that the performance of the Contract is contrary to the international sanctions enforced in the Republic of Lithuania, the Contract may be terminated unilaterally by the Customer, without any period of notice being required.

  - In the event of unilateral termination of the Contract on the grounds set out in the Contract, the Customer shall pay the Contractor price to the Contractor only for the part of the Works properly performed at the rates provided for in the Contract.

  - If the Contract is terminated by the Customer due to its improper performance by the Contractor, the latter must reimburse the Customer for all costs incurred in completing the Works under the Contract as a result of such termination and must compensate the Customer for any losses incurred as a result of the termination, including losses due to the cost of the Works, and loss of income to the Customer if the Contractor’s refusal to perform the Contract prevents the completion of the Object on time.

  - Termination of the Contract shall not affect the validity of the terms and conditions of the Contract governing liability, dispute resolution procedure and other terms and conditions of the Contract, provided that such terms and conditions according to their nature survive the termination of the Contract.

12.SUBCONTRACTING AND JOINT ACTIVITIES

12.1. The Contractor intends to use the following subcontractors for the performance of the Works (including the provision of services and supplies covered by the performance of the Works) under this paragraph: ________________________________________________________(This paragraph shall be completed if the Contractor has specified in the tender the part of the Works to be subcontracted and the subcontractors to be engaged).

12.2. Upon conclusion of the Contract, but not later than the commencement of its performance, the Contractor undertakes to inform the Customer of the contact details and representatives of the subcontractors referred to in paragraph 12.1 of the Contract. The Contractor also undertakes to keep the Customer informed of any changes to this information throughout the performance of the Contract.

12.3. The Contractor may, during the period of performance of the Contract  , for the Works which, as specified by the Contractor n the tender, would be assigned to subcontractors, change the subcontractor used or engage an additional subcontractor without changing the subcontractors used (hereinafter - the additional subcontractor).

12.4. The Contractor shall be entitled to use a new subcontractor during the period of performance of the Contract, even if it did not foresee the use of subcontractors for the relevant part of the Services at the time of the submission of the tender (hereinafter - the new subcontractor”), if during the period of performance of the Contract material circumstances arise which make such use necessary and which a prudent Contractor could not have anticipated, including, without limitation, the cases where:

12.4.1. the Contractor’s machinery required for the performance of the Works breaks down and the Contractor is unable to repair or, due to weather conditions or other reasons, is unable to bring replacement machinery or other necessary equipment to the area where the Works are to be performed within a time period exceeding 30 (thirty) days, or such other time period as may be specified by the Contractor, which would materially interfere with the performance of the Works in accordance with the specified time limits;

12.4.2. the aim is to avoid the potential collapse of a structure;

12.4.3. due to the needs of economic activities by port users in the Works area, where cargo handling activities are planned before the completion of the Works, which require the desired result of the Works as set out in the technical design, and the Contractor will not be able to complete the Works within the time limit due to such particularities of the port user’s economic activity;;

12.4.4. the purpose is to complete the Works within the specified time limit and it is necessary to increase the efficiency of the Works, or where the Customer reasonably requests earlier completion of the Works;

12.4.5. the Contract is modified or additional Works are procured on the grounds set out in Article 97(1)(2) to (5) and (2) of the Law;

12.4.6. in the event of any other circumstances in the Contractor’s organisational structure or business operations that are material to the performance of the Works.

12.5. If the Contractor wishes to replace the subcontractor, to use an additional subcontractor or a new subcontractor, it must inform the Customer in writing in advance of the intended change or the use of the additional or new subcontractor and provide evidence of the qualifications of the replacing, additional or new subcontractor (if the subcontractors were subject to qualification requirements or the right to carry out the Works for which the new subcontractor is being used is linked to the qualification requirements), and of the absence of grounds for exclusion (where the Contractor has relied on the capability of the subcontractor being replaced or where the Contract provides for the Customer’s right to require subcontractors to provide proof of the absence of grounds for exclusion), and the contact details and representatives of the replacing, additional or new subcontractor. In order to use a new subcontractor, the Contractor must additionally state the reasons for using the new subcontractor.

12.6. The Customer must, upon receipt of the Contractor’s request and all documents, verify, within 7 (seven) working days of receipt of all documents, whether (where applicable) the subcontractor’s qualifications meet the requirements set out in the procurement documents and whether there are grounds for compulsory exclusion of the subcontractor. Once the Parties have fulfilled all the conditions set out in this paragraph they shall conclude an agreement on the amendment to the Contract.

12.7. If the Contractor replaces a subcontractor, uses an additional or a new subcontractor in violation of the procedure prescribed by the Contract, the Contractor shall, at the request of the Customer, immediately refuse the services of such subcontractor and shall replace it with a suitable subcontractor in accordance with the procedure prescribed by the Contract.

12.8. The Contractor must immediately withdraw from any subcontractor who is subject to international sanctions or other restrictions and ensure that such subcontractor does not perform the Contract from the time of the imposition of the sanctions or other restrictions on it and, if necessary, replace such subcontractor with another subcontractor in the manner prescribed by the Contract.

12.9. If, during the performance of the procurement, the qualifications of the Contractor and/or the subcontractor have not been verified for the right to engage in the relevant activities or have been verified to an incomplete extent, the Contractor shall undertake to the Customer that the Contract will be performed by only those persons who are so qualified. At the request of the Customer, the Contractor shall provide the Customer with documents proving the subcontractor’s right to carry out the relevant activities.

12.10. The Contractor shall be liable for its own and its subcontractors’ work and the quality and safety of the work, for failure to perform or improper performance of its obligations, and for direct damages caused by the fault of its subcontractors.

12.11. If the Contractor engages subcontractor(s) to perform the Contract, a trilateral direct settlement agreement may be signed between the Customer, the Contractor and the subcontractor, describing the procedure for direct settlement with the subcontractor. The Customer shall, no later than 3 (three) working days after the entry into force of the Contract and receipt from the Contractor of the contact details of the subcontractor referred to in paragraph 12.2 of the Contract, and in the case of a change of a subcontractor, use of an additional or new subcontractor in accordance with the procedure laid down in the Contract – from the date of the Customer’s consent to the change of the subcontractor to the Contractor, inform the subcontractor in writing of the possibility of direct settlement, and the subcontractor shall submit a written request to the Customer to enter into a tripartite settlement agreement in order to make use of this possibility. No advance payment may be made to the subcontractor, and direct payment to the subcontractor may only be made after the Customer has accepted the subcontractor’s work from the Contractor in accordance with the procedures set out in the Contract. The trilateral agreement shall not be in conflict with the provisions of the Contract and the procurement documents, and shall also provide for the Contractor’s right to object to unjustified payments to the subcontractor. In the event of a dispute between the Contractor and a subcontractor, they shall resolve the dispute independently, without the participation of the Customer. The amounts payable to the Contractor shall be reduced by the amounts paid to the subcontractor

12.12. Where the Contract is awarded to a Contractor who represents economic entities acting on the basis of a joint operating agreement, the terms and conditions regarding joint activity set out in the procurement documents shall apply to the Contractor: [to be specified when concluding the Contract].

13.PROVISION OF GUARANTEES FOR THE WORKS

13.1. The Contractor warrants that its Works shall, throughout the Warranty Period, conform to the characteristics set out in the Project, the Contract Documents, the requirements of the normative construction documents, and shall be free from defects which would invalidate or impair their value or fitness for their intended use.

13.2. If any defects in the Object are identified by the Customer within the Warranty Period, the Customer must bring claims to the Contractor within a reasonable period of time from the date of their identification. The Contractor shall remedy any defects in the Works arising during the Warranty Period for free within the time limit agreed between the Contractor and the Customer, which shall be determined taking into account the scope of the Works.

13.3. If the Contractor is more than 15 (fifteen) days behind the expiry of the time limit set by the Customer for rectification of the defects in the Works, or if it becomes apparent that the Contractor will not rectify the defects in the Works satisfactorily, the Customer shall have the right to entrust the Works to a third party.

13.4. If the Contractor refuses to remedy defects or other deficiencies in the Works, the Customer shall remedy them. The Contractor shall be deemed to have refused to remedy defects or other work deficiencies, or fails to start eliminating them within 15 (fifteen) days of the Customer's written request to eliminate the deficiencies.

13.5. In the cases provided for in paragraph 13.4 of the Contract, the Contractor must pay the Customer for the performed elimination of defects or other deficiencies within 15 (fifteen) days of sending the invoice.

13.6. The warranty period shall be 5 (five) years for the Object, 10 (ten) years for concealed elements (of the Object) and 20 (twenty) years for deliberately concealed defects.

13.7. For materials, products and components provided by the Contractor, the warranty period shall be 5 (five) years.

13.8. The Contractor shall submit to the Customer, together with the certificate of handover of the construction works completed the Contractor, a document securing the fulfilment of the obligations of the warranty period according to the Contract. This document shall ensure payment to the Customer of the costs of elimination of defects caused by the fault of the Contractor during the first 3 (three) years of the warranty period of the building in the event of the Contractor's insolvency or bankruptcy. The amount securing the elimination of defects during the 3 (three) year warranty period must be at least 5 (five) per cent of the construction cost of the building. The document securing the fulfilment of the Contractor's obligations under the Contract during the warranty period must be an irrevocable, first demand, unconditional letter of guarantee issued by an insurance company or by a bank of good standing with at least Standard & Poor's - BBB+-, or Moody's - Baa1, or Fitch - BBB+ credit rating (or such rating should be issued to its parent bank).

.

14.LIABILITY OF THE PARTIES

14.1. If the Customer unreasonably delays payment for the Works within the prescribed time limit, the Customer shall, at the Contractor's request, pay to the Contractor a default interest of 0.05 (five hundredths of one) per cent of the overdue amount for each day of delay, but not more than 10 (ten) per cent of the initial value of the Contract. Unreasonable delay shall not include suspension of the performance of the Contract in the manner prescribed therein.

14.2. If the Contractor fails to complete the Works within the time limit for the performance of the Works or fails to submit the mandatory Construction Documents within the time limit set for the completion of the Works and the handing over of the completed Works, on request of the Customer, the Contractor must pay, for each day of delay, a default interest of 0.05 % (five one-hundredths of one per cent) of the Contract Price, excl. VAT, but not exceeding 10 % (ten per cent) of the initial value of the Contract value, and to indemnify the Customer for any losses incurred by reason of the delay, which is not covered by the default interest.

14.3. If the Contractor fails to provide the Customer with an agreed calendar schedule for the performance of the Works within the time limit set out in the Contract, the Contractor shall be liable, at the request of the Customer, to pay a fine of EUR 300 (three hundred euro) for each day of delay from the end of the time limit set out in the Contract for the submission of such schedule.

14.4. In the event of non-compliance with the Customer’s instructions to perform the Works, the Contractor shall, at the Customer’s request, be liable to pay a fine of EUR 100 (one hundred euro) for each failure to comply with an instruction by the date set by the Customer.

14.5. Where the Contractor conceals the fact of the discovery of the necessary Works, from the discovery of which the Contractor should have been aware of the circumstances necessitating the additional works, the Contractor must pay a fine of 10% of the estimated price of the necessary additional works excluding VAT. The cost of the necessary additional works shall be calculated in accordance with the established procedure for the calculation of the cost of additional works.

14.6. If, during the performance of the Works, the Contractor or a person engaged by the Contractor is found to be under the influence of alcohol or narcotic drugs, psychotropic or toxic substances, the Contractor shall pay a fine of EUR 1,500 (one thousand five hundred euro) for each case found or for the person’s refusal to be tested for being under the influence of alcohol or other substances. The fine specified in this paragraph shall be applied on the basis of notifications from the competent control authorities of the Republic of Lithuania with confirmed data or from the Port Authority. A person is considered to be under the influence of alcohol if the level of alcohol in the body exceeds 0.00 ppm.

14.7. If the Contract is terminated through the fault of one of the Parties, the Party at fault shall pay to the other Party a fine of 10% of the initial value of the Contract.

14.8. If the Contractor breaches the obligation to comply with the environmental protection requirements set out in subparagraph 8.3.7 and 8.3.11 of the Contract, the Contractor shall the Customer a fine of EUR 1,000.00 (one thousand euro) for each case of such breach, irrespective of whether the Contractor has been subjected to any economic sanctions, civil, administrative or criminal liability by the state environmental control authorities and officials for non-compliance with environmental protection requirements. The fine provided for in this paragraph shall be applied on the basis of reports from the competent control authorities of the Republic of Lithuania with confirmed data or reports from the representatives of the Port Authority, when the infringement has been recorded by technical equipment in the possession of the Port Authority (or by other persons on its behalf). Except in cases of notifications by the competent control authorities of the Republic of Lithuania, the Contractor shall be deemed to be in breach of the obligation to comply with the environmental protection requirements under subparagraphs 8.3.7 and 8.3.11 of the Contract, if the technical equipment available to the Customer (or other persons acting on its behalf) detects an exceedance of the limit values for noise, air, water, soil pollution set by the environmental protection standards or any other non-compliance with environmental protection requirements.

14.9. By signing the Contract, the Parties acknowledge that the default interest and fines specified in the Contract shall be the minimum losses agreed by the Parties for delayed implementation of the Contract which need not to be proved by the Parties.

14.10. If it is not clear what has caused the delay in the performance of the Contract, or if there are no apparent unlawful acts of the Parties in causing the delay in the performance of the Contract, the Parties may separately agree on the amount of the liability to be imposed under the Contract.

14.11. Invoices submitted for default interest, fines and compensation for losses shall be paid within 7 (seven) days, unless the Customer specifies a different deadline in writing. The Customer has the right to deduct any unpaid interest, fines, and other reasonably claimed amounts from the payments due to the Contractor. These deductions will be made in accordance with the unilateral set-off procedure outlined in the Civil Code of the Republic of Lithuania. Alternatively, the Customer may direct these claims to the Contract performance security document, provided that the Contract obligates the Contractor to furnish such a document.

14.12. The Contractor shall be fully liable for violations of the laws of the Republic of Lithuania regulating the protection of the environment and for damages caused to third parties and their property during the performance of the Works under the Contract.

14.13. The Contractor warrants that its activities under the Contract will not give rise to any legitimate third party claims by the Customer for infringement of patents, copyrights or other proprietary rights.

14.14. If the result of the Work, or any part thereof, is accidentally destroyed or damaged before it is handed over to the Customer, or if it becomes impossible to complete the Work due to the fault of the Contractor, the Contractor shall not be entitled to claim compensation for the Works. The Contractor shall bear the risks of the above circumstances.

14.15. If the Contractor performs the Works in an unauthorised manner and/or deviates from the normative construction documents within the meaning of paragraph 4.8 of the Contract, the Contractor shall be liable to the Customer with its own funds:

14.15.1. where the deviation from the normative construction documents may result in additional costs for the Customer to remedy such an outcome of the Works carried out by the Contractor;

14.15.2. where the Customer suffers damage as specified in the Contract or otherwise as a result of the deviation from the normative construction documents.

15.FORCE MAJEURE CIRCUMSTANCES

15.1. The Party shall not be held liable for any full or partial non-fulfilment of its obligations under the Contract if the Party can demonstrate that it is due to unusual circumstances beyond the Party's reasonable control and which the Party could not reasonably anticipate, avoid or eliminate by any means, such as: Decisions of the Government of the Republic of Lithuania and other acts affecting business of the Parties, political disturbances, strikes, declared and undeclared wars, other armed conflicts, fires, floods and other natural disasters. Force majeure shall be deemed to be the circumstances referred to in Article 6.212 of the Civil Code of the Republic of Lithuania and in the Rules on Exemption from Liability in the Event of Force Majeure approved by Resolution No 840 of the Government of the Republic of Lithuania of 15 July 1996. When determining the circumstances of force majeure, the Parties shall be guided by the Resolution of the Government of the Republic of Lithuania No 222 of 13 March 1997 on approval of the procedure for issuing certificates attesting to force majeure. In the event of force majeure, the Parties to the Contract shall be exempted from liability for the full or partial non-fulfilment or improper fulfilment of their obligations under the Contract according to the procedure laid down by legal acts of the Republic of Lithuania, and the time limit for the fulfilment of the obligations shall be extended.

15.2. The Party requesting to be relieved of liability must notify the other Party in writing of the force majeure as soon as possible, but not later than within 3 (three) working days after the occurrence or discovery of such circumstances, providing evidence that it has taken all reasonable precautions and made every effort to minimize the costs or adverse consequences, and of the likely time limit for the fulfilment of its obligations. Notification shall also be required when the grounds for the non-fulfilment of the obligations cease to exist. If the Party fails to give timely notice or to inform, it must compensate the other Party for any damage suffered by the other Party as a result of the failure to give timely notice or to inform.

16.CORRESPONDENCE AND PERSONS RESPONSIBLE FOR THE PERFORMANCE

OF THE CONTRACT

16.1. The correspondence between the Parties shall be in Lithuanian. All notices, consents, instructions and other communications which the Party may provide under the Contract shall be deemed valid and duly served if given in writing to the other Party or sent by post, fax or email to the addresses set out below, or to such fax numbers or other addresses as may be specified by a Party when giving notice:

| Customer | Contractor |
| --- | --- |
| Joint Stock Company Klaipėda State Seaport Authority |  |
| J. Janonio g. 24-1, LT-92251 Klaipėda |  |
| +370 46 499 799 |  |
| info@port.lt |  |

16.2. The Customer shall appoint as its representative(s) the responsible person(s) ________________, tel. [__________], email [_________] in the Object, who shall be responsible for the performance of the Contract and shall have the right to resolve any technical problems relating to the supervision and performance of the Contract, but shall not have the right to modify the Contract, either orally or by conduct.

16.3. The Contractor shall designate an authorised person as its representative at the Object and shall notify the Customer in writing within 5 (five) working days after the entry into force of the Contract (indicating a direct contact telephone number and a direct e-mail address). The Contractor’s representative shall have the right and authority to resolve any technical problems relating to the performance of the Contract and to sign documents relating thereto on behalf of the Contractor.

16.4. The Parties shall have the right to unilaterally change the responsible persons specified in the Contract or, in accordance with the provisions of the Contract, responsible persons specified in the Parties’ notifications to the other Party, by informing the other Party immediately, but not later than within 5 (five) days, using the contacts specified in paragraph 16.1. Any claims by a Party arising out of or in connection with improperly served notices will be deemed unfounded.

17.FINAL PROVISIONS

17.1. The Contract shall be drawn up in the Lithuanian language in two copies of equal legal force, one for each Party or, in the case of an electronic document, signed by both Parties with an electronic signature. Where the Contract or any other instrument provided for therein is signed with a qualified electronic signature, it shall be drawn up according to requirements of the Specification of the Electronic Document Signed by Electronic Signatures ADOC-V1.0 approved by Order No V-60 of the Chief Archivist of Lithuania of 7 September 2009.

17.2. If any provision of the Contract is invalid, it shall not invalidate the Contract as a whole, except where the Parties would not have entered into the Contract at all without that provision. If any provision or rule of the Contract becomes invalid in whole or in part, it shall not invalidate the remaining provisions or rules of the Contract. In that case, the Parties agree to make their best efforts to replace the invalid provision or standard with a legally effective one that, as far as possible, incorporates the functions of the invalid provision or standard and has an equivalent effect.

17.3. Time limits set out in the Contract in days shall be calculated in calendar days, unless otherwise specified in the Contract.

17.4. The Contractor shall be exempted from Klaipėda State Seaport dues: ship, navigation, quay, tonnage, sanitary and passenger charges as stipulated by the Regulations for Klaipėda State Seaport Dues (as subsequently amended) approved by Order No V-236 of the of the Director General of Klaipėda State Seaport Authority of 27 December 2022 This provision shall not apply if the Contract is not performed through the fault of the Contractor.

17.5. The Contract shall be governed by the RL law. Disputes arising between the Parties in connection with the Contract shall be settled by negotiation or, in the event of failure to reach an agreement by negotiation, by judicial dispute resolution procedure before courts of the Republic of Lithuania. In the event of a dispute between the Parties, the Works under the Contract shall not be suspended and the Contractor shall be obliged to complete the Works.

17.6. The Parties confirm that they have read the Contract, understood its contents and consequences, accepted it as being in accordance with their aims and signed it.

17.7. The Annexes to the Contract shall form an integral part thereof. Annexes to the Contract:

17.7.1. Annex 1 - Bill of Quantities and Prices for Works, 1 page.

17.7.2. Annex 2 - Completed Works Acceptance and Handover Certificate, 2 sheets.

18. LEGAL PARTICULARS AND SIGNATURES OF THE PARTIES

| For the Customer | For the Contractor |
| --- | --- |
| Joint Stock Company Klaipėda State Seaport Authority |  |
| Legal entity code 240329870 |  |
| J. Janonio g. 24-1, 92251 Klaipėda |  |
| Tel. (8 46) 499 799 |  |
| E-mail: info@port.lt |  |
| VAT code LT 403298716 |  |
| S/A LT14 7300 0100 3488 9443 |  |
| Swedbank AB, bank code 73000 |  |
| CEO General Place of seal |  |
| Algis Latakas |  |