To the tenderers of the procurement				2026-02-20

(sent by the CPP IS means)

| Procurement number in the CPP IS | 6190568 |
| --- | --- |
| Method or tool of the procurement | Negotiated procedure with publication of a contract notice |
| Lot of the object of the procurement |  |
| Name of the procurement | 32328 Services for the installation of locomotive safety systems (LSS) on track vehicles |

*hereinafter collectively referred to as the “Procurement”

REQUEST FOR CLARIFICATION OF THE PROCUREMENT DOCUMENTS

Following the requirements and procedure established in the Terms and Conditions of the Procurement, having examined the request for clarification of the Procurement documents submitted by the interested supplier(s) by the CPP IS correspondence means, UAB LTG Kompetencijų centras provides the following answers(s):

| Seq. No | Question/request* | Answer** |
| --- | --- | --- |
|  | After a detailed review of the tender requirements, we kindly ask you to extend the contract execution period to 4 months. This request is related to the need to conduct a survey of the rolling stock, prepare installation documentation for our system, develop design documentation for components (cables, connectors, etc.), as well as manufacture, implement, and test the system. | We take note of the request and set the contract period at 6 months, i.e. 4 months for the provision of the services and 2 months for the final payment. Clause 11.1 of the Specific Part of the Contract is amended to read as follows: 11.1. The Contract shall remain in force until the obligations have been fulfilled in full (until the value of the Initial Contract has been exhausted), but the term shall not exceed 6 (six) months. The period for the provision of the Services shall be 4 (four) months plus 2 months for final payment. The clauses in Section 6 of the Technical Specifications shall be updated accordingly to read as follows: 1) 5.21. The LSS and its maintenance equipment shall be delivered to Vilkpėdės g. 2B, Vilnius (check before delivery) for installation in SSGR no later than 90 calendar days after the entry into force of the Contract. 2) 5.22. The installation, training and static and dynamic testing of the LSS in SSGR shall be carried out by the Supplier in accordance with a service schedule mutually agreed between the Supplier and the Client, but no later than within 105 calendar days after the entry into force of the Contract. 3) 5.28. The Supplier shall deliver a test programme and methodology, agreed in advance with the Client, no later than within 20 calendar days after the entry into force of the Contract. |
|  | Additionally, due to the changes made to the tender documentation, we kindly request an extension of the tender submission deadline until 20 February 2026. | Information on the changed time limit for the submission of the Initial tenders shall be provided through the CPP IS. |

* The text of the request(s) for clarification/adjustment of the Procurement documents submitted by the interested supplier(s) is not edited. In case of any possible inaccuracies, the text in the original language shall prevail.

** Clarification/ adjustment and its provisions prevail over earlier provisions set out in the Procurement documents.

In the light of the fact that the Technical Specification of the Procurement is adjusted later than 4 days left to the final date of submission of Initial tenders, the time limit for submission of the Initial tenders extended.

Enclosed:

- Service contract special conditions EN;

- Technical specification EN.