Contract for the Supply of Services Annex 1

SYSTEM FOR THE PREPARATION OF TASKS FOR VBE PUPIL ACHIEVEMENT ASSESSMENTS, INCLUDING THE PREPARATION, TESTING AND QUALITY ASSURANCE OF TASKS, TECHNICAL SPECIFICATION FOR THE PROCUREMENT OF SERVICES

- GENERAL INFORMATION

  - Contracting authority: National Education Agency (hereinafter – CA).

  - Information about the project: Project ‘Strengthening learning-supportive assessment of achievement and progress’ No. 10-062-P-0001 (hereinafter – the Project) is being implemented in accordance with Contract No. PPS-240 signed on 31 July 2024 between the Central Project Management Agency and the National Education Agency. The main objectives of the project are the practical testing of innovative formative assessment tools in the educational process, the introduction of quality parameters into summative assessment procedures, and international cooperation in developing task resources based on the methodology of test theory. In order to strengthen learning-oriented assessment of achievement and progress through the implementation of updated curricula, by providing support to teachers and improving their competencies in task design and performance assessment, the preparation of multi-stage external pupil achievement assessment tasks and assessment guidelines for secondary education is planned. The target group for this activity comprises teaching staff (excluding staff at higher education institutions), staff of the National Education Agency, and other specialists within the education system.

  - The purpose of the procurement is to create a system for the preparation of pupil achievement assessment tasks, covering the preparation, testing and quality assurance of state maturity examination (hereinafter – SME) tasks (hereinafter – the Model).

  - The Model must consist of the following main parts:

    - a description of the preparation of student achievement assessment tasks (covering the preparation, testing and quality assurance of tasks) (hereinafter referred to as the Model Description);

    - a plan for the implementation of the Model Description and the roll-out of the Model (stages, timetable) (hereinafter referred to as the Plan);

    - a methodology for ensuring the quality of tasks (hereinafter referred to as the Methodology).

  - The procurement is not divided into lots, as the services being procured relate to the creation of a single integrated model (system); the components of the services (services for the preparation of the Model Description, the Implementation and Deployment Plan, and the Task Quality Assurance Methodology) are closely interrelated. The decision not to split the procurement is based on the need to procure high-quality services in a rational and efficient manner.

  - Green procurement is being implemented. Only intangible (intellectual) services are being procured, not related to the creation of a physical object, the provision of which is not expected to have a significant negative impact on the environment, does not create a source of pollution and does not generate waste.

- GENERAL REQUIREMENTS

  - The service provider (hereinafter – the Provider) must ensure confidentiality throughout the entire term of the Contract, and after the Contract has expired, until state maturity examinations are organised. The results of the Contract created during the performance of the service, namely the Model and the Model description, shall be considered confidential information. The Service Provider shall not have the right to publish on or otherwise disclose or transfer to third parties, except in the case provided for in this clause, information and/or data learned or transferred to it during the performance of the Contract, nor shall it have the right to use the information and/or data received for the performance of the Contract for personal or third-party purposes. All information and/or data provided to the Supplier by the PO, or information and/or data learned during the performance of the Contract, shall be treated as confidential. The confidentiality obligations set out in this clause shall not apply to the disclosure of information and/or data obtained during the performance of the Contract where such disclosure is required by the laws of the Republic of Lithuania.

  - The Provider must ensure the security of the personal data of persons participating in the activities in accordance with the requirements of the General Data Protection Regulation (Regulation (EU) 2016/679 of the European Parliament and of the Council of 27 April 2016 ‘on the protection of natural persons with regard to the processing of personal data and on the free movement of such data, and repealing Directive 95/46/EC’).

  - The provider must ensure compliance with information security requirements in accordance with applicable legislation.

  - The provider must ensure compliance with EU investment communication and visibility requirements. The plan prepared by Lithuania was adopted by a decision of the European Council on 28 July 2021. The use of the EU emblem must be ensured: ‘Use of the EU emblem in the implementation of EU programmes 2021–2027’: https://2021.esinvesticijos.lt/dokumentai/es-emblemos-naudojimas-vykdant-2021-2027-m-es.

  - The Provider is responsible for the copyright of the text, image and audio material used. This is in accordance with Order No. V-755 of the Minister of Education, Science and Sport of the Republic of Lithuania, dated 26 June 2019 (as amended by Order No. V-836 of the Minister of Education, Science and Sport of the Republic of Lithuania dated 25 May 2022). When providing services, the Provider is liable for the visual, textual and audio material, designs, patents, trade names, trademarks and signs, source code, computers and software, interfaces, and other objects of copyright, related rights or industrial property rights, the Provider shall be responsible for obtaining the relevant rights, necessary permissions, licences and other required rights. The Client may require the Provider to provide evidence of the acquisition of the necessary permits, licences and other rights required to provide the Services and/or to use the works created.

  - All results of the provision of services recorded during the performance of the Contract and the related rights acquired in the course of performing the Contract, including all economic copyright and other intellectual or industrial property rights specified in Article 15 of the Law on Copyright and Related Rights of the Republic of Lithuania , with the exception of personal non-property rights to the results of intellectual activity, shall be the property of the PO, which the PO may use, publish, transfer, adapt or assign as it deems appropriate, without any geographical or other restrictions. The Supplier may not publish articles about the services and/or disclose information received from the PO without the PO’s prior written consent. The Supplier shall indemnify the PO against any claims arising from the use of copyright, patents, licences, drawings, designs, trade names or trademarks, except where such infringement is attributable to the PO.

  - When preparing the Model, the horizontal principles, the Charter of Fundamental Rights of the European Union, the provisions of the United Nations Convention on the Rights

of Persons with Disabilities must be observed, ensuring equal opportunities and non-discrimination, as well as compliance with the principles of universal design.

  - The Model must be based on the following documents, which shall be provided to the Supplier upon request after the Contract has been signed: Description of the Procedure for the Organisation and Conduct of State Matriculation Examinations, approved by Order No. V-1187 of the Minister of Education, Science and Sport of the Republic of Lithuania of 11 September 2023 ‘On the Approval of the Description of the Procedure for the Organisation and Conduct of State Matriculation Examinations’ (current version); Description of the procedures for the preparation and quality control of state final examination questions; General curricula for pre-school, primary, lower secondary and upper secondary education, approved by Order No. V-1269 of the Minister of Education, Science s and Sport of the Republic of Lithuania of 24 August 2022 ‘On the Approval of General Curricula for Pre-school, Primary, Lower Secondary and Upper Secondary Education’; Description of tasks for state final examinations in languages, the description of tasks for the state final examinations in mathematics, natural sciences, informatics and engineering technologies, and the description of tasks for the state final examinations in social studies were approved by Order No. VK-909 (current version).

  - The model must be drafted in correct Lithuanian, in accordance with the requirements of the standard language.

- GENERAL INFORMATION ON THE CONTEXT OF THE PROCUREMENT

  - External assessments of pupils’ achievements in secondary education are an integral part of the Lithuanian education system. They are used to assess pupils’ achievements upon completion of the secondary education programme, and the results of the state maturity examinations (hereinafter – VBE) are used to calculate the competitive score for admission to higher-level educational institutions in Lithuania. Given the significance of VBE results and the opportunities they define for continuing education at a higher level, the transparency of the organisation of external assessments of secondary school pupils’ achievements, the clarity of processes, and the quality assurance of VBE tasks are of paramount importance for the smooth functioning of the system and the public interest.

  - In Lithuania, the current institutional structure is such that processes related to VBE are essentially concentrated in a single institution – the National Education Agency (hereinafter – NEA) – within a single department. Despite the accumulated expert knowledge, defined responsibilities and obligations, the NEA faces the challenge of insufficient internal human resources and bears a heavy administrative burden (in organising public procurement), therefore, functions related to the content of task preparation suffer.

  - It should also be noted that, under the current procedure, the head of the NŠA approves the VBE tasks for all subjects. There is no institutionalised practice of involving other relevant institutions in the approval of tasks. This would allow the NŠA to share responsibility for approving VBE tasks, help ensure the quality of VBE tasks and strengthen public confidence in the VBE.

  - Currently, VBE tasks are prepared in just under a year (including procurement procedures), however, to ensure their quality, additional quality assurance procedures and appropriate tools are required (e.g., organising pilot tests of the tasks being developed, a mechanism for standardising results and compensating for population differences, which includes tools for its implementation). The implementation of these procedures involves a task development cycle lasting longer than one or two years.

  - Question setters represent another area of challenge for the VBE – exam question setters work only for a limited period, and their services are procured through public procurement. Due to the limited supply of question writers, question-writing teams usually

consist of two people. Furthermore, it is currently not possible to involve teachers of final-year classes in question setting, as the questions are published in the same year and there is a risk regarding the confidentiality of the questions. Extending the exam paper preparation cycle and enabling teachers of Year 11 and 12 students to be involved in the preparation of exam papers would create the conditions to address the issue of the limited supply of potential exam paper setters.

- SPECIAL REQUIREMENTS FOR THE PREPARATION OF THE MODEL

  - The provider must prepare a description of the Model, which must include:

    - a discussion of its purpose and objectives, an explanation of the structure of the Model description, and a presentation of the content sections;

    - an analysis of the processes in Lithuania related to the preparation of tasks for pupil achievement assessments and the assurance of their quality (situation analysis), highlighting strengths and weaknesses, and suggesting areas and processes for improvement;

    - taking into account the identified problem areas in Lithuania, the practices of models for the preparation of pupil achievement assessment tasks, including task testing and quality assurance, were examined and presented in at least three European countries whose education systems are similar to that of Lithuania. When selecting foreign countries, regional diversity must be ensured (Northern Europe, Southern Europe, Central and/or Eastern Europe, Western Europe);

    - taking into account the analysis of the practices, assess the advantages and disadvantages of each practice presented (paying particular attention to the overall concept of the practice, its stages, processes, participants, the duration, scope and distribution of processes and stages throughout the calendar year), provide a reasoned recommendation and propose the most suitable option for the preparation of pupil achievement assessment tasks and the assurance of their quality in Lithuania. The proposed Model is intended to help ensure the preparation of pupil achievement assessment tasks in a simple, clear and transparent manner;

    - the multi-stage task preparation cycle of the proposed Model, its stages and components, the duration and scope of each stage, the participating institutions and their characteristics (e.g. in the case of schools, account must be taken of school types, the founding body, the language of instruction and regional representation);

    - describe and explain in detail the processes of the multi-stage task development cycle, explaining the hierarchy and interaction of participants: the roles, functions and responsibilities, quality assurance processes and their benefits, the main risks of the multi-stage task development cycle that need to be managed, and the human and administrative resources required for each stage of the multi-stage task development cycle (the PO will provide preliminary estimates);

    - A job description for the VBE task developer coordinator has been prepared, and the role and responsibilities of the task developer coordinator within the context of the multi-stage task preparation cycle have been explained and presented;

    - The methods, responsibilities, contracting procedures and scope for the selection of VBE task developers have been prepared and described. A description of the organisation and coordination of this process has been provided, setting out the responsibilities of the persons (institutions) supervising the process and the number of participants. The tenderer must present two alternatives for the selection of VBE task developers and contracts with task developers, and discuss the advantages, disadvantages and risks of each possible alternative. The tenderer must highlight the legal restrictions when concluding contracts with task developers under Employment Contracts and Service Procurement Contracts;

    - specify the requirements for members of the VBE task force (experience,

qualifications), its composition, present the principles for forming the group, and the principles for organising the successful integration of the group and (new) members into the task preparation process, taking into account that the examinations are held in Years 11 and 12 of secondary school, and that VBE tasks are prepared in parts, with the final task being formed from separately prepared parts;

    - the external structure (e.g. examination boards) with which the NŠA could cooperate and share responsibility for approving VBE tasks has been established and described, including its composition, distribution of functions and responsibilities, selection procedure, and scope. A description of the organisation and coordination of this process has been provided, setting out the responsibilities of the persons (institutions) supervising the process, the number of participants, and the prepared rules of procedure or regulations;

    - The principles and procedures for the formation of the task bank are set out, proposed and presented in detail, including the responsibilities of those involved in the procedures and the decision-making process regarding the inclusion of tasks in the task bank. When describing the principles for the formation of the bank, the processes for recording the parameters and metadata of statistical tasks and their organisation are included and presented in detail;

    - A job description for the psychometrist and statistician involved in the multi-stage item development cycle has been drawn up and outlined, and the qualification requirements and contracting procedures have been set out; the roles of the psychometrician and statistician have been explained and presented, including at which stage of the task development cycle they become involved and what their responsibilities are within the context of the multi-stage task development cycle; the organisation and procedure for their involvement in the task development cycle have been explained;

    - if the proposed Model introduces other new positions that do not currently exist within the Contracting Authority, the Supplier must provide descriptions of these;

    - The Supplier must propose and provide a reasoned justification in the Model as to which parts of the multi-stage task preparation cycle processes should be procured externally and which should be implemented within the PO.

  - The following requirements must be taken into account when preparing the Plan:

    - when preparing the Model description and submitting the Model recommendation to Lithuania, the Supplier must provide a Model implementation plan and specify therein what specific steps the responsible authorities should take and what decisions they should make in order for the Model to be implemented. The Model implementation plan must describe how the functions and tasks of the NŠA should be redistributed among its individual departments (and/or other institutions, e.g. the Ministry of Education and Science, subject teachers’ associations, expert councils), specifying the scope of human resources and the relevant mutual coordination mechanism and responsibilities;

    - when submitting the Model Implementation Plan, the Supplier must take into account the documents currently regulating the preparation of pupil achievement assessment tasks (including testing and quality assurance) currently governing such tasks, and clearly specify in the Model Implementation Plan which documents (legislation) and how they should be amended in order to transition to the proposed Model. The risks associated with the implementation of the Model must be specified;

    - The Provider must include an implementation plan for the Model Description in the Model Description. When describing the multi-stage task preparation cycle, its stages and all the processes and participants involved, the Supplier must provide a detailed presentation and justification of the duration of the multi-stage task preparation cycle and attach a clearly prepared timetable. The implementation plan for the Model Description must also include a detailed presentation of the financial resources (preliminary calculations to be

provided by the Contracting Authority) required for the implementation of the Model Description, along with an assessment and adjustment of these resources in line with necessary requirements. The risks associated with the implementation of the Model must be identified, as well as the problems to be addressed by applying the new Model.

  - Before preparing the Model, the Supplier must carry out a preliminary analysis of experiences in European countries regarding the preparation of tasks for assessing pupils’ achievements, and submit a preliminary concept of the Model (hereinafter – the Model concept) to the PO. It must include:

    - the conclusions and summaries of the analysis carried out, as well as a detailed discussion and analysis of the experiences of three European countries proposed in the Model. A justification must be provided as to which country’s experience will be used as a basis for preparing the Model description and the Methodology;

    - a presentation of the methods to be used and the information relevant to the Lithuanian examination context to be collected during the situation analysis;

    - an example of the organisation and coordination of a single selected stage of task preparation and quality assurance is provided for the future Model description, discussing the responsibilities of the persons (institutions) supervising the process, human resources and other information relevant to the process.

  - When drafting the model description and the Plan, the Supplier shall consult with staff designated by the Contracting Authority (e.g., by organising round-table discussions, workshops or focus groups with staff from the Contracting Authority’s Performance Department, during which current practices regarding task preparation and quality assurance are reviewed, the PO’s needs and problem areas, involving parties and/or their representatives participating in the processes in the consultations). Consultations are held at the PO’s premises or in the virtual environment specified at .

  - The Provider shall organise regular (at least once a month) meetings with staff designated by the PO (staff of the Achievements Department) and present to them the progress made in preparing the Model Description and the Plan. The Provider must take into account the feedback provided by the PO during the meetings. Meetings are held remotely or at the PO’s premises.

  - The Provider must organise at least 8 informational working meetings on the Model for staff designated by the PO (Achievements Department staff) and stakeholders (at least one information meeting to present the concept of the Model; the section of the Model description covering the comparative analysis and the proposed Model for Lithuania; the section of the Model description covering the description of task preparation participants and the task bank; the Model implementation plan; the implementation plan for the Model description; at least 3 meetings to present the prepared Model description and Plan). Information meetings shall be held at the PO’s premises or in the specified virtual environment. Presentations must be prepared in Lithuanian and English.

  - The Supplier must prepare the methodological part of the Model – the Methodology. The Methodology presents and describes in detail the methods proposed for testing tasks and ensuring task quality.

    - It must be ensured that the methods help to construct valid, varied tasks that facilitate the assessment of pupils’ achievements, taking into account Lithuania’s national curricula, examination procedures, the diversity of pupils (including those with special educational needs), the country’s cultural context;

    - the purpose of each method, the necessary conditions for its application, limitations and subject-specific recommendations are presented;

    - the statistical parameters collected, their purpose, data sources and the tools to be used for their calculation are presented in detail and comprehensively. When presenting

statistical parameters, their calculation is provided and explained, taking into account the statistical/mathematical analysis software used by the PO, or by specifying other software, including open-source and free statistical analysis software. Recommendations for assessing and interpreting their reliability are provided. The methodology must include both classical and modern test theory methods and statistical parameters;

    - account must be taken of the fact that some examination tasks in Lithuania are digital, and the specific nature of quality assurance must be assessed;

    - specific examples and/or drafts (templates) of report forms for the collected data and the results of their analysis must be provided and presented.

  - Before preparing the Methodology, the Supplier must familiarise themselves with the Lithuanian examination context and submit a preliminary concept of the Methodology (hereinafter – the Methodology Concept). It must include:

    - at least one example of a method for testing tasks and ensuring quality, statistical parameters, calculations and instruments used must be presented and described for the relevant section of the Methodology. A justification of their relevance and usefulness must be provided.

  - During the preparation of the Methodology, the Supplier shall consult with staff designated by the PO (e.g., organise round-table discussions, workshops or focus groups with staff from the PO’s Achievement Department, during which the current practices for task preparation and quality assurance shall be refined, the PO’s needs and problem areas, involving parties and/or their representatives participating in the processes in the consultations). Consultations are held at the PO’s premises or in a designated virtual environment.

  - The Supplier shall organise regular (at least once a month) meetings with staff designated by the PO (staff of the Achievements Department) and present to them the progress made in developing the Methodology. The Supplier must take into account the feedback provided by the PO’s staff during the meetings. Meetings are held remotely or at the PO’s premises.

  - The Provider must organise at least 4 information meetings on the Methodology for staff designated by the PO (Achievements Department staff) and interested parties (at least 1 information meeting to present the concept of the Methodology and the initial draft of the Methodology, and at least 2 meetings to present the finalised Methodology. Information meetings are held at the PO’s premises or in the specified virtual environment. Presentations must be prepared in Lithuanian and English .

- GENERAL REQUIREMENTS

  - The template must include the title of the project being implemented by the PO – ‘Strengthening the assessment of learning outcomes and progress’ – and the mandatory publicity logos: the European Union emblem with the statement: “Funded by the European Union” (hereinafter – the logo), the MA’s logo, available on the website https://www.nsa.smm.lt/apie-nsa/nsa-logotipas/, the logo of the Ministry of Education, Science and Sport of the Republic of Lithuania, available on the website https://smsm.lrv.lt/lt/administracine-informacija/ministerijos-logotipas.

  - The final version of the Model shall be submitted to the PO, laid out and edited by the PO, and uploaded to the environment specified by the PO.

  - The Supplier must provide all documents required for uploading to the specified environment, if requested.

  - Requirements for the digital design of the Model:

    - must be agreed with the PO;

    - the layout of the content must allow the user to navigate easily and comfortably

and meet universal design requirements for font size, text layout and colour scheme, but must not hinder work with the material;

    - the content and text font must comply with the design agreed with the PO and be easily legible both on a computer screen and on smart devices;

    - The template must use high-quality visual and graphic elements and visualisations: at least one graphic/visual or other element on each page, and these must be consistent with the theme of the content.

  - The template must be submitted in correct Lithuanian or English, in .pdf and .docx formats, neatly laid out and edited, using 12-point Times New Roman font with 1.5 line spacing and standard margins. It must include a title page, table of contents and all other parts of the publication specified in sub-clause 4.1, and must comply with the requirements of Chapters 4 and 5.

  - The model must consist of an introduction, a main body organised into thematic chapters, a conclusion, appendices, a glossary of terms, a list of references and sources, and a title page, title, and table of contents. The main body must constitute at least 80 per cent of the total volume of the Model.

  - The summary of the Model description, the implementation of the Model description and the Model implementation plan must include a brief and reader-friendly summary. Recommendations for the implementation of the Model, summary conclusions and other relevant information are provided. The Model description, the implementation of the Model description and the Model implementation plan must be presented graphically, using diagrams and infographics, to visually convey the essence of the Model.

  - When preparing the concept for the Model and Methodology, examples of illustrations, diagrams or other visual material to be used in the preparation of the Model and Methodology shall be provided. The concept shall be no less than 12 A4 pages in length, in accordance with the requirements set out in Sections 4 and 5.

- SERVICE DELIVERY TERMS

  - Duration of service provision: 23 months. Coordination and approval of the service provision schedule:

    - Within 3 working days of the Contract being signed, the Supplier shall hold a joint meeting with the Contracting Authority to agree on the services to be provided and to appoint a contact person with whom all service delivery procedures will be coordinated.

    - Within 3 working days of the meeting, the Supplier must draw up a service delivery schedule and submit it to the PO. The schedule shall set out the planned work and deadlines, as well as any planned meetings with the PO (in person and/or remotely). The PO shall approve the schedule within 2 working days. Once the Client has provided feedback, the Service Provider shall amend the schedule in accordance with the comments received within 2 working days and submit it to the Client for final approval.

  - Preparation and coordination of the model concept with the Client:

    - The Supplier must prepare and submit the Model Concept no later than 1.5 months after the signing of the Contract.

    - The Supplier must present the Model Concept to the staff designated by the PO and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Upon receipt of the Client’s comments, the Supplier shall amend the Model Concept in accordance with the comments received within 3 working days and submit it to the Client for final approval. The Client shall approve the Model Concept within 3 working days. If the PO does not approve the revised version and returns it for further amendment, the Supplier

must amend the Model Concept within 3 working days.

  - Preparation and coordination with the PO of the version of the Model description covering points 4.1.1–4.1.6 (hereinafter – Comparative Analysis and Proposed Model for Lithuania ):

    - Upon approval of the Model concept, the Supplier shall, within 2.5 months at the latest, prepare the Comparative Analysis and the proposed Model for Lithuania and submit it to the Contracting Authority.

    - The Supplier must present the Comparative Analysis and the proposed Model for Lithuania to the staff members designated by the Contracting Authority and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Once the Contracting Authority has provided its comments, the Supplier shall amend the Comparative Analysis and the proposed Model for Lithuania in accordance with the comments received within 3 working days and submit them to the Contracting Authority. If the Contracting Authority does not approve the revised version and returns it for further amendment, the Supplier must amend the Comparative Analysis and the proposed Model for Lithuania within 3 working days.

  - Preparation and coordination with the Contracting Authority of the version of the Model description covering points 4.1.7–4.1.14 (hereinafter – the description of task preparation participants and the task bank):

    - Upon approval of the Comparative Analysis and the proposed Model for Lithuania, the Supplier shall, within 1.5 months at the latest, prepare the description of task preparation participants and the task bank and submit it to the Contracting Authority.

    - The Supplier must present the description of the task preparation participants and the task bank to the staff members designated by the Contracting Authority and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Upon receipt of the Contracting Authority’s comments, the Supplier shall amend the description of the task preparation participants and the task bank in accordance with the comments provided within 3 working days and submit it to the Contracting Authority. If the Contracting Authority does not approve the revised version and returns it for further amendment, the Supplier must amend the description of the task preparation participants and the task bank within 3 working days.

  - Preparation and coordination with the Contracting Authority of the plan covering points 4.2.1–4.2.2 (hereinafter referred to as the Model Implementation Plan):

    - Upon approval of the description of the task preparation participants and the task bank, the Supplier shall, within 1.5 months at the latest, prepare the Model Implementation Plan and submit it to the PO.

    - The Supplier must present the Model Implementation Plan to the staff members designated by the Contracting Authority and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Upon receipt of the Client’s comments, the Supplier shall amend the Model Implementation Plan in accordance with the comments provided within 3 working days and submit it to the Client. If the Client does not approve the amended version and returns it for further revision via , the Supplier must amend the Model Implementation Plan within 3 working days.

  - Preparation and coordination with the PO of a version of the Model Description Implementation Plan covering point 4.2.3:

    - Upon approval of the Model Implementation Plan, the Supplier shall prepare the Model Description Implementation Plan within 1.5 months at the latest and submit it to the

PO.

    - The Supplier must present the Model Description Implementation Plan to the

staff designated by the Contracting Authority, together with the Comparative Analysis and the proposed Model for Lithuania, and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Once the PO has provided its comments, the Supplier shall amend the Model Description Implementation Plan in accordance with the comments received within 3 working days and submit it to the PO. If the PO does not approve the amended version and returns it for further revision, the Supplier must amend the Model Description Implementation Plan within 3 working days.

  - Preparation of the final version of the Model Description and Plan and coordination with the PO :

    - Once the PO has approved all parts of the Model Description and Plan, the Supplier shall, within 1 month of their approval, prepare the Final version of the Model Description and Plan and submit it to the PO.

    - The Supplier must present the Final Model Description and Plan variant to the staff members designated by the PO and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Upon receipt of the Client’s comments, the Supplier shall amend the Final Model Description and Plan in accordance with the comments received within 3 working days and submit it to the Client. If the PO does not approve the revised version and returns it for further revision, the Supplier must amend the Final Model Description and Plan within 3 working days.

    - If the PO determines that the quality of the services provided for the preparation of the Model does not meet the requirements set out in Section 4 for Model preparation services during the Model preparation stages listed in Section 5 (excluding the stage of submission of the Final Model), the Provider shall replace the expert(s) with another expert(s) who meets the qualifications of the previous expert(s). The Contracting Authority shall inform the Supplier of the inadequately provided services and the Supplier shall replace the expert(s) within 10 working days of receiving such information.

    - If the Contracting Authority determines that the Model prepared by the Supplier does not meet the requirements set out in this technical specification and (or) the quality of the Model’s preparation does not meet the conditions and requirements specified in this technical specification, the Contracting Authority shall have the right to refuse to accept the prepared Model.

  - The Supplier shall organise at least 3 working meetings for the employees designated by the Contracting Authority and interested parties, at which it shall present the prepared Model description and Plan no later than 1 month after the approval of the final version of the Model description and Plan.

  - Preparation of the methodology concept and coordination with the Contracting Authority:

    - The Contractor must prepare and submit the draft methodology no later than

1.5 months after the Contracting Authority has approved the final Model Description and Plan.

    - The Supplier must present the Methodology Concept to the staff members designated by the PO and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Upon receipt of the Client’s comments, the Supplier shall amend the Methodology Concept in accordance with the comments received within 3 working days and submit it to the Client for final approval. The Client shall approve the Methodology Concept within 3 working days. If the Contracting Authority does not approve the revised version and

returns it for further amendment, the Supplier must amend the draft Methodology within 3 working days.

  - Preparation of the initial version of the Methodology (points 4.7.1–4.7.5, excluding detailed statistical parameter calculations) (hereinafter referred to as the ‘Initial Version of the Methodology’) and its coordination with the PO:

    - Once the PO has approved the Methodology concept, the Supplier shall, no later than 2 months from its approval, prepare the Initial Version of the Methodology and submit it to the PO.

    - The Supplier must present the Initial Version of the Methodology to the staff members designated by the PO and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Once the PO has provided its comments, the Provider shall amend the Draft Methodology in accordance with the comments received within 3 working days and submit it to the PO. If the PO does not approve the amended version and returns it for further revision, the Provider must amend the Draft Methodology within 3 working days.

  - Preparation of the Final Methodology and coordination with the Contracting Authority:

    - Once the PO has approved the Initial Methodology Version, the Supplier shall, no later than 2.5 months from its approval, prepare the Final Methodology Version (covering points 4.7.1–4.7.5 and detailed calculations of statistical parameters) and submit it to the PO.

    - The Supplier must present the Final Version of the Methodology to the staff members designated by the Contracting Authority and, within 3 working days, collect their suggestions and comments and/or confirmation that it has been prepared correctly.

    - Once the Contracting Authority has provided its comments, the Supplier shall amend the Final Version of the Methodology in accordance with the comments received within 3 working days and submit it to the Contracting Authority. If the Contracting Authority does not approve the amended version and returns it for further revision, the Supplier must amend the Final Version of the Methodology within 3 working days.

  - The Supplier shall organise at least 3 working meetings for the staff designated by the PO and interested parties, at which the prepared Methodology shall be presented no later than 1 month after the approval of the Final Version of the Methodology.

  - The Supplier shall organise at least 3 technical meetings for staff designated by the Contracting Authority and interested parties, at which the prepared Model shall be presented.

  - The Supplier shall be responsible for the quality of the content, including its technical accuracy, compliance with legislation and the requirements of these technical specifications.

  - The services must be provided throughout the duration of the Contract.

| Structural part of the Model | Stage | Deliverables | Deadline | Payment |
| --- | --- | --- | --- | --- |
| Model description; Methodology; Plan. | Stage I | Agreed and approved service delivery schedule | 2 weeks after signing the Contract |  |
| Model description | Stage II | Model concept prepared and agreed with the Contracting Authority | 1.5 months after signing the Contract |  |

|  |  |  | 0.5 months for coordination |  |
| --- | --- | --- | --- | --- |
| Model description | Stage III | Comparative analysis completed and agreed with the PO, and a proposed Model for Lithuania | 2.5 months after approval of the model concept |  |
|  |  |  | 0.5 months for coordination |  |
| Model description | Stage IV | Description of task preparation participants and the task bank prepared and agreed with the PO | 1.5 months after approval of the comparative analysis and the model proposed by for Lithuania | Payment – 25% of the contract price |
|  |  |  | 0.5 months for coordination |  |
| Plan | Stage V | Model implementation plan prepared and agreed with the contracting authority | 1.5 months following approval of the list of participants in the task preparation and the description of the task bank |  |
|  |  |  | 0.5 months for coordination |  |
| Plan | Stage VI | Model Description Implementation Plan prepared and agreed with the PO | 1.5 months after approval of the Model implementation plan |  |
|  |  |  | 0.5 months for coordination |  |
| Model description; Plan | Stage VII | Final version of the Model Description and Plan prepared and agreed with the PO | 1 month after approval of all parts |  |
|  |  |  | 0.5 months for coordination |  |
| Model description; Plan | Stage VIII | Model Description and Plan presented | 1 month after approval of the final Model description and Plan variant | Payment – 25% of the contract price |
| Methodology | Stage IX | Methodology concept prepared and agreed with the Contracting Authority | 1.5 months after approval of the Final Model Description and Plan variant |  |
|  |  |  | 0.5 months for coordination |  |

| Methodology | Stage X | Preliminary version of the Methodology prepared and agreed with the PO | 2 months after approval of the Methodology concept | Payment – 20% of the contract price |
| --- | --- | --- | --- | --- |
|  |  |  | 0.5 months for coordination |  |
| Methodology | Stage XI | Final version of the Methodology prepared and agreed with the PO | 2.5 months after approval of the initial version of the methodology |  |
|  |  |  | 0.5 months of coordination with the |  |
| Methodology | Stage XII | The prepared Methodology has been presented | 1 month after approval of the final version of the methodology |  |
| All Model documents | Stage XIII | Presentations of the Model to stakeholder groups | 1 month after the Methodology presentations |  |
|  |  |  |  | Final payment – 30% of the Contract price |

  - Procedure for submitting results: the results for each point shall be submitted to the person specified in the project Contract who is responsible for the performance of the Contract.

  - The Supplier shall be paid in instalments: 25% of the contract value – upon the Supplier’s completion of the tasks for Stages I–IV and the Contracting Authority’s approval of their completion; 25% of the contract value – upon the Supplier’s completion of the tasks for Stages V–VIII and the Contracting Authority’s approval of their completion; 20% of the contract value – upon the Supplier completing the tasks of stages IX–X and the Contracting Authority confirming their completion; 30% of the contract value – upon the Supplier providing all services specified in the Contract and the Contracting Authority confirming their completion.

  - Deviations from the service deadlines specified in clause 6.15 (in general) are permitted for no more than 1 week. The service delivery schedule may be adjusted at the Contracting Authority’s initiative during the course of the work.